## Sheet1
TIP Amendments - Birmingham MPO
Since October 2023
Project Sponsor | Action Requested | Project Reference Number | Federal Aid Number | Funding Source | Scope | Description | Fiscal Year | Conformity Status* | Federal Estimated Cost | State/Local Estimated Cost | Total Estimated Cost | MPO Approval Date
ALDOT | Move to FY2024 | 100047786 | NH-I065() | National Highway System | UT | ADD LANES ON I-65 FROM SR-3 (US-31) NORTH OF CALERA TO SOUTH OF CR-87 AND BRIDGE REPLACEMENT OVER CSX RAILROAD (BINS 006484 AND 006485) | 2024 | Non-Exempt* | 60029.6 | 15007.4 | 75037 | 2023-11-08
ALDOT | Move to FY2024 | 100047486 | NH-I065() | National Highway System | CN | ADD LANES ON I-65 FROM SR-3 (US-31) NORTH OF CALERA TO SOUTH OF CR-87 AND BRIDGE REPLACEMENT OVER CSX RAILROAD (BINS 006484 AND 006485) | 2024 | Non-Exempt* | 31215488 | 7803872 | 39019360 | 2023-11-08
ALDOT | Move to FY2024 | 100044964 | NH-I065() | National Highway System | UT | I-65 ADD LANES FROM 0.2 MILE SOUTH OF CR-87 TO .56 MILE SOUTH OF BUCK CREEK | 2024 | Non-Exempt* | 119658.4 | 29914.6 | 149573 | 2023-11-08
ALDOT | Move to FY2025 | 100044963 | NH-I065() | National Highway System | CN | I-65 ADD LANES FROM 0.2 MILE SOUTH OF CR-87 TO .56 MILE SOUTH OF BUCK CREEK | 2025 | Non-Exempt* | 54412815.2 | 13603203.8 | 68016019 | 2023-11-08
ALDOT | Add new project | 100077390 | NH-0079() | National Highway System | PE | ADDITIONAL LANES ON SR-79 FROM 0.30 MILE SOUTH OF MP 14.00 TO 0.30 MILE NORTH OF MP 15.00 | 2024 | Non-Exempt* | 200000 | 50000 | 250000 | 2023-11-08
ALDOT | Add new project | 100075699 | NH-0079() | National Highway System | RW | ADDITIONAL LANES ON SR-79 FROM 0.30 MILE SOUTH OF MP 14.00 TO 0.30 MILE NORTH OF MP 15.00 | 2024 | Non-Exempt* | 200000 | 50000 | 250000 | 2023-11-08
ALDOT | Add new project | 100075698 | NH-0079() | National Highway System | UT | ADDITIONAL LANES ON SR-79 FROM 0.30 MILE SOUTH OF MP 14.00 TO 0.30 MILE NORTH OF MP 15.00 | 2024 | Non-Exempt* | 404000 | 101000 | 505000 | 2023-11-08
ALDOT | Add new project | 100075696 | NH-0079() | National Highway System | CN | ADDITIONAL LANES ON SR-79 FROM 0.30 MILE SOUTH OF MP 14.00 TO 0.30 MILE NORTH OF MP 15.00 | 2025 | Non-Exempt* | 8080000 | 2020000 | 10100000 | 2023-11-08
ALDOT | Add new project | 100077462 | IM-I459() | Interstate Maintenance | PE | SIGN REPLACEMENT ON I-459 FROM I-59/20 (EXIT 1) TO I-59 (EXIT 33). | 2024 | Exempt | 136350 | 15150 | 151500 | 2023-11-08
ALDOT | Add new project | 100077463 | IM-I459() | Interstate Maintenance | CN | SIGN REPLACEMENT ON I-459 FROM I-59/20 (EXIT 1) TO I-59 (EXIT 33). | 2024 | Exempt | 3150000 | 350000 | 3500000 | 2023-11-08
ALDOT | Add new project | 100077406 | ST-037-I59-016 | State Funds | PE | LIGHTING REHABILITATION ON I-59 FROM THE 3RD AVE N OVERPASS TO THE I-459 INTERCHANGE | 2024 | Exempt | 0 | 300000 | 300000 | 2023-11-08
ALDOT | Add new project | 100077735 | ST-058-888-007 | State Funds | CN | TEMPORARY TRAFFIC SIGNAL AT THE INTERCHANGE OF I-20 AND KELLY CREEK ROAD | 2024 | Exempt | 0 | 300000 | 300000 | 2023-11-08
ALDOT | Add new project | 100077470 | ST-037-888-013 | State Funds | CN | HARMER STREET BRIDGE REPLACEMENT OVER VALLEY CREEK, INCLUDING RESURFACING HARMER STREET FROM SR-5 (US-11) TO HUNTSVILLE AVENUE | 2024 | Exempt | 0 | 1000000 | 1000000 | 2023-11-08
ALDOT | Add new project | 100069670 | BR-I059() | Bridge Funds | PE | BRIDGE REPLACEMENT ON I-59 NB (BIN #007232) AND SB (BIN #007231) OVER CANOE CREEK | 2024 | Exempt | 718008 | 179502 | 897510 | 2023-11-08
ALDOT | Add new project | 100069671 | BR-I059() | Bridge Funds | CN | BRIDGE REPLACEMENT ON I-59 NB (BIN #007232) AND SB (BIN #007231) OVER CANOE CREEK | 2027 | Exempt | 7397643.2 | 1849410.8 | 9247054 | 2023-11-08
Chelsea | Add new project | 100077750 | TAPAA-TA24(924) | Transportation Alternative Program - Any Area | CN | PEDESTRIAN AND STREETSCAPE IMPROVEMENTS ALONG CHESSER PLANTATION LANE FROM THE CHESSER PLANTATION NEIGHBORHOOD TO CHESSER DRIVE AND ALONG CHESSER DRIVE FROM CHESSER PLANTATION LANE TO ATCHISON DRIVE IN THE CITY OF CHELSEA | 2024 | Exempt | 800000 | 200000 | 1000000 | 2023-11-08
Calera | Add new project | 100077743 | TAPAA-TA24(923) | Transportation Alternative Program - Any Area | CN | DOWNTOWN STREETSCAPE IMPROVEMENTS ALONG MAIN STREET (SR-25) FROM US-31 TO THE CSX RR AND ALONG US-31 FROM MAIN STREET TO 17TH AVENUE IN THE CITY OF CALERA | 2024 | Exempt | 800000 | 200000 | 1000000 | 2023-11-08
City of Birmingham | Add new project | 100077733 | TAPAA-TA24(921) | Transportation Alternative Program - Any Area | CN | TWO-WAY SEPARATED CYCLE TRACK ON 15TH AVENUE NORTH FROM CARRAWAY BOULEVARD/US-31 TO THE INTERSECTION OF NORWOOD BOULEVARD/28TH NORTH IN THE CITY OF BIRMINGHAM | 2024 | Exempt | 800000 | 200000 | 1000000 | 2023-11-08
City of Birmingham | Delete phase | 100067026 | CMAQ-3717() | Congestion Mitigation Air Quality (CMAQ) | PE | STREETSCAPE IMPROVEMENTS ALONG 4TH AVE N FROM 16TH ST N TO 18TH ST N ALONG 17TH ST FROM 4TH AVE N TO 5TH AVE N AND ALONG 16TH ST FROM 1ST AVE N TO I-59/20 | 2024 | Exempt | 185454.4 | 46363.6 | 231818 | 2023-11-08
City of Birmingham | Delete phase | 100067027 | CMAQ-3717() | Congestion Mitigation Air Quality (CMAQ) | UT | STREETSCAPE IMPROVEMENTS ALONG 4TH AVE N FROM 16TH ST N TO 18TH ST N ALONG 17TH ST FROM 4TH AVE N TO 5TH AVE N AND ALONG 16TH ST FROM 1ST AVE N TO I-59/20 | 2024 | Exempt | 41212 | 10303 | 51515 | 2023-11-08
City of Birmingham | Change description and increase funding | 100067028 | CMAQ-3717() | Congestion Mitigation Air Quality (CMAQ) | CN | BIRMINGHAM CIVIL RIGHTS CROSSROADS: RECONNECTING HISTORIC NEIGHBORHOODS THROUGH ACTIVE MOBILITY | 2024 | Exempt | 1842666 | 460666.5 | 2303332.5 | 2023-11-08
City of West Jefferson | Add new project | 100076384 | RALG-37-2023-515 | Rebuild Alabama | CN | RESURFACING HONEYSUCKLE ROAD, BRIAR ROAD, CHESTNUT ROAD, AND WOODLAND ROAD, CITY OF WEST JEFFERSON (0.60 MILES) | 2024 | Exempt | 0 | 175000 | 175000 | 2023-11-08
Mountain Brook | Add $184,800 of STPBH funds | 100066110 | STPBH-3716(256) | Surface Transportation Birmingham Attributable | PE | BRIDGE REPLACEMENT (BIN 012869) ON OLD BROOK TRAIL OVER LITTLE SHADES CREEK AND BRIDGE REHABILITATION (BIN 002873) ON CANTERBURY ROAD OVER WATKINS CREEK | 2017 | Exempt | 522268 | 130567 | 652835 | 2023-11-08
Mountain Brook | Add $160,000 of CMAQ funds | 100064199 | CMAQ-3715(266) | Congestion Mitigation Air Quality (CMAQ) | PE | INTERSECTION IMPROVEMENTS: INSTALLATION OF ROUNDABOUT AT THE CAHABA RD/CULVER RD/LANE PARK RD INTERSECTION AND RESTRIPING SR-38 (US-280) RAMPS-CITY OF MOUNTAIN BROOK | 2017 | Exempt | 850712.8 | 212678.2 | 1063391 | 2023-11-08
Mountain Brook | Add $120,000 of CMAQ funds | 100068123 | CMAQ-3718(251) | Congestion Mitigation Air Quality (CMAQ) | PE | SIDEWALKS ALONG PINE RIDGE ROAD FROM OVERBROOK ROAD TO OLD LEEDS ROAD | 2019 | Exempt | 316513.6 | 79128.4 | 395642 | 2023-11-08
Mountain Brook | Add $200,000 of CMAQ funds | 100068125 | CMAQ-3718(251) | Congestion Mitigation Air Quality (CMAQ) | RW | SIDEWALKS ALONG PINE RIDGE ROAD FROM OVERBROOK ROAD TO OLD LEEDS ROAD | 2024 | Exempt | 402000 | 100500 | 502500 | 2023-11-08
Montevallo | Add new project | 100076850 | ATRP2-59-2023-348 | ATRIP2 | CN | INTERSECTION IMPROVEMENTS AT SR-119 AND CR-22, INCLUDING LEFT TURN LANES ON SR-119 AND CR-22; SPONSOR - MONTEVALLO | 2024 | Exempt | 0 | 1977041 | 1977041 | 2023-11-08
Calera | Add new project | 100076849 | ATRP2-59-2023-126 | ATRIP2 | CN | INTERSECTION IMPROVEMENTS AT I-65 AND SR-25 INTERCHANGE (EXIT 228), INCLUDING RESTRIPING SB EXIT RAMP TO ADD RIGHT TURN LANE, ADDING RIGHT TURN LANE ONTO NB ENTRANCE RAMP AND A NEW TRAFFIC SIGNAL; SPONSOR - CALERA | 2024 | Exempt | 0 | 1048325 | 1048325 | 2023-11-08
Argo | Add new project | 100076846 | ATRP2-58-2023-083 | ATRIP2 | CN | INTERSECTION IMPROVEMENTS AT SR-7 (US-11) AND CR-6 (ARGO- MARGARET ROAD), INCLUDING LEFT/ RIGHT TURN LANES ON US-11 AND RIGHT TURN LANE ON CR-6; SPONSOR - ARGO | 2024 | Exempt | 0 | 1980000 | 1980000 | 2023-11-08
Moody | Add new project | 100076852 | ATRP2-58-2023-350 | ATRIP2 | CN | INTERSECTION IMPROVEMENTS ON SR-25 (US-411) AT WASHINGTON DRIVE/ VERBENA DRIVE AND AT HIGH SCHOOL DRIVE, INCLUDING LEFT/ RIGHT TURN LANES AND NEW TRAFFIC SIGNALS; SPONSOR - MOODY | 2024 | Exempt | 0 | 1724656 | 1724656 | 2023-11-08
BJCTA | Add new project | 100077901 | TBD | Congestion Mitigation Air Quality (CMAQ) | CN | Construct Two Bus Rapid Transit Stations - Inbound and Outbound on 1st Avenue North and 20th Street | 2024 | Exempt | 640000 | 160000 | 800000 | 2023-11-08
ALDOT | Change description | 100058461 | ACNHF-1602(555) | Appalachian Development Highway System | RW | BIRMINGHAM NORTHERN BELTLINE FROM CUNNINGHAM CR. TO SR-79 GRADE/DRAIN/BASEPAVE/BRIDGE (PARTIAL) | 2024 | Non-Exempt* | 3800000 | 0 | 3800000 | 2024-02-14
ALDOT | Change description | 100058462 | ACNHF-1602(555) | Appalachian Development Highway System | UT | BIRMINGHAM NORTHERN BELTLINE FROM CUNNINGHAM CR. TO SR-79 GRADE/DRAIN/BASEPAVE/BRIDGE (PARTIAL) | 2025 | Non-Exempt* | 2000000 | 0 | 2000000 | 2024-02-14
ALDOT | Add a New Project | 100076970 | NH-0150() | National Highway System | PE | ADD LANES ON SR-150 FROM SHANNON ROAD TO WEST OF SHADES CREEK (PHASE 2) | 2026 | Non-Exempt* | 824240.8 | 206060.2 | 1030301 | 2024-02-14
ALDOT | Add a New Project | 100077619 | IM-I059() | Interstate Maintenance | CN | REPAIR AND REPLACEMENTS OF ENTRANCE AND EXIT RAMPS ON I-59/20 AT MCASHAN DRIVE | 2024 | Exempt | 1800000 | 200000 | 2000000 | 2024-02-14
ALDOT | Add a New Project | 100077797 | ST-037-I59-017 | State Funds | RW | INTERCHANGE IMPROVEMENTS AT I-59/20 EXIT 104 (MCASHAN DRIVE) TO INLCUDE NEW OVERPASS STRUCUTRES OVER I-59/20 AND DIVERGING DIAMOND INTERSECTION AT NB/SB RAMPS | 2024 | Exempt | 0 | 200000 | 200000 | 2024-02-14
ALDOT | Add a New Project | 100078263 | NH-038() | National Highway System | PE | INTERSECTION IMPROVEMNTS ON SR-38 (US-280) FROM EAST OF GRANDVIEW PARKWAY TO WEST OF RESOURCE CENTER PARKWAY | 2024 | Exempt | 400000 | 100000 | 500000 | 2024-02-14
ALDOT | Add a New Project | 100077796 | ST-037-459-003 | State Funds | RW | NEW INTERCHANGE ON I-459 NEAR MP 9, INLCUDES AUXILARY LANES FROM THE NEW INTERCHNAGE TO EXIT 10, BRIDGES OVER I-459 AND RAMP BRIDGES OVER THE RAILROAD, CITY OF HOOVER | 2024 | Non-Exempt* | 0 | 750000 | 750000 | 2024-02-14
ALDOT | Change description | 100055334 | IMF-I065() | Interstate Maintenance | PE | ADDITIONAL LANE AND BRIDGE REPLACEMENT ON I-65 FROM .56 MILES S OF BUCK CRK TO 1 MILE N OF SR-3 (US-31) IN ALABASTER OVER CSX RR (BIN 006489 AND 006490) OVER CR-26 (BIN 006491 AND 006492) AND OVER OLD US-31 AND CSX RR (BIN 006493 AND 006494) | 2024 | Non-Exempt* | 1336809.6 | 148534.4 | 1485344 | 2024-02-14
ALDOT | Change description | 100055335 | IMF-I065() | Interstate Maintenance | CN | ADDITIONAL LANE AND BRIDGE REPLACEMENT ON I-65 FROM .56 MILES S OF BUCK CRK TO 1 MILE N OF SR-3 (US-31) IN ALABASTER OVER CSX RR (BIN 006489 AND 006490) OVER CR-26 (BIN 006491 AND 006492) AND OVER OLD US-31 AND CSX RR (BIN 006493 AND 006494) | 2024 | Non-Exempt* | 12707558.1 | 1411950.9 | 14119509 | 2024-02-14
ALDOT | Delete Project | 100055333 | IMF-I065() | Interstate Maintenance | CN | BRIDGE WIDENING ON I-65 OVER L AND N RAILROAD, 0.8 MILE NORTH OF SR-3 (US-31) IN CALERA, BIN #006484 AND #006485 | 2026 | Non-Exempt* | 3908551.5 | 434283.5 | 4342835 | 2024-02-14
ALDOT | Delete Project | 100056427 | NH-0003() | National Highway System | CN | SLOPE STABILIZATION ON SR-3 (US-31) AT BROOKWOOD MEDICAL CENTER DRIVE | 2024 | Exempt | 94634.4 | 23658.6 | 118293 | 2024-02-14
BJCTA | Add new project | 100076677 | tbd | FTA Grant | TR | TRANSIT ORIENTED DEVELOPMENT PILOT PROGRAM | 2024 | Exempt | 1600000 | 400000 | 2000000 | 2024-02-14
Mountain Brook | Add $360,000 of CMAQ funds | 100068123 | CMAQ-3718(251) | Congestion Mitigation Air Quality (CMAQ) | PE | SIDEWALKS ALONG PINE RIDGE ROAD FROM OVERBROOK ROAD TO OLD LEEDS ROAD | 2019 | Exempt | 676513.6 | 169128.4 | 845642 | 2024-02-14
RPCGB | Add new project | tbd | tbd | Carbon Reduction Program | TR | FLEXIBLE FUNDS TRANSFER TO FTA 5310 FOR CLASTRAN OPERATING EXPENSES | 2025 | Exempt | 450000 | 450000 | 900000 | 2024-02-14
RPCGB | Add new project | tbd | tbd | Carbon Reduction Program | TR | FLEXIBLE FUNDS TRANSFER TO FTA 5310 FOR CAPITAL PROJECTS | 2025 | Exempt | 550000 | 137500 | 687500 | 2024-02-14