## Sheet1
TIP Amendments - Birmingham MPO
Since September 2019 - MPO Policy Committee
Project Sponsor | Action Requested | Project Reference Number | Federal Aid Number | Funding Source | Scope | Description | Fiscal Year | Conformity Status* | Federal Estimated Cost | State/Local Estimated Cost | Total Estimated Cost | MPO Approval Date
ALDOT | Add New Project | 100070835 | IM-I065() | Interstate Maintenance | PE | PLANING OVERLAY AND STRIPING ON I-65 FROM THE CR-52 OVERPASS TO THE SOUTH END OF THE CAHABA RIVER BRIDGE | 2020 | Non-Exempt* | 272700 | 30300 | 303000 | 2019-11-13
ALDOT | Add New Project | 100070839 | IM-I065() | Interstate Maintenance | CN | PLANING OVERLAY AND STRIPING ON I-65 FROM THE CR-52 OVERPASS TO THE SOUTH END OF THE CAHABA RIVER BRIDGE | 2020 | Non-Exempt* | 6363000 | 707000 | 7070000 | 2019-11-13
Shelby County | Move to FY2024 | 100067603 | STPBH-5918() | Surface Transportation Program - Birmingham | PE | RESURFACING ON CR-17 (VALLEYDALE ROAD) FROM I-65 TO CR-29 (CALDWELL MILL ROAD) AND ON CR-43 (BEAR CREEK ROAD) FROM SR-38 (US-280) TO SR-25 | 2024 | Exempt | 80000 | 20000 | 100000 | 2019-11-13
Shelby County | Move to FY2024 | 100067607 | STPBH-5918() | Surface Transportation Program - Birmingham | CN | RESURFACING ON CR-17 (VALLEYDALE ROAD) FROM I-65 TO CR-29 (CALDWELL MILL ROAD) AND ON CR-43 (BEAR CREEK ROAD) FROM SR-38 (US-280) TO SR-25 | 2024 | Exempt | 1200000 | 300000 | 1500000 | 2019-11-13
Jefferson County | Move to FY2024 | 100056488 | STPBH-3715(255) | Surface Transportation Program - Birmingham | UT | GALLERIA BOULEVARD EXTENSION FROM CR-458 (LORNA ROAD) TO SR-150 | 2024 | Non-Exempt* | 400000 | 100000 | 500000 | 2019-11-13
Jefferson County | Move to FY2024 | 100056489 | STPBH-3715(255) | Surface Transportation Program - Birmingham | CN | GALLERIA BOULEVARD EXTENSION FROM CR-458 (LORNA ROAD) TO SR-150 | 2024 | Non-Exempt* | 3200000 | 800000 | 4000000 | 2019-11-13
St. Clair County | Add RW Phase | 100070989 | to be determined | Congestion Mitigation Air Quality (CMAQ) | RW | INTERSECTION IMPROVEMENTS ON SR-25(US-411) AT PARK AVENUE | 2020 | Exempt | 40000 | 10000 | 50000 | 2019-11-13
St. Clair County | Add RW Phase | 100070990 | to be determined | Congestion Mitigation Air Quality (CMAQ) | RW | INTERSECTION IMPROVEMENTS ON SR-25(US-411) AT CR-6 (SANIE ROAD/SIMPSON ROAD) | 2020 | Exempt | 180000 | 45000 | 225000 | 2019-11-13
Bessemer | Add $300,000 of MPO TAP funds | 100068368 | TAPAA-TA18(913) | $638,301 of TAP Any Area - $300,000 of MPO TAP | CN | MULTI-USE TRAIL EXTENSION PEDESTRIAN BRIDGE AND ADA COMPLIANT ACCESS RAMP ALONG SR-150 ON AN ABANDONED RAILROAD BETWEEN BERKLEY AVENUE AND CAROLINA AVENUE | 2020 | Exempt | 938301 | 234575.25 | 1172876.25 | 2019-11-13
ALDOT | Add New Project | 100069858 | IM-I065() | Interstate Maintenance | PE | PAVEMENT REHABILITATION ON I-65 FROM WALKER CHAPEL ROAD INTERCHANGE TO CR-112 (MOUNT OLIVE ROAD INTERCHANGE) | 2020 | Exempt | 245430 | 27270 | 272700 | 2020-03-11
ALDOT | Add New Project | 100069859 | IM-I065() | Interstate Maintenance | CN | PAVEMENT REHABILITATION ON I-65 FROM WALKER CHAPEL ROAD INTERCHANGE TO CR-112 (MOUNT OLIVE ROAD INTERCHANGE) | 2020 | Exempt | 2454300 | 272700 | 2727000 | 2020-03-11
ALDOT | Add New Project | 100068226 | IM-I459() | Interstate Maintenance | PE | CONCRETE PAVEMENT REHABILITATION ON I-459 FROM SR-3 (US-31) TO LORNA ROAD | 2020 | Exempt | 222771.6 | 24752.4 | 247524 | 2020-03-11
ALDOT | Add New Project | 100068227 | IM-I459() | Interstate Maintenance | CN | CONCRETE PAVEMENT REHABILITATION ON I-459 FROM SR-3 (US-31) TO LORNA ROAD | 2020 | Exempt | 1818000 | 202000 | 2020000 | 2020-03-11
Bessemer | Delete Project | 100064749 | RHCH-RR16(912) | Safety | CN | RAILROAD CROSSING IMPROVEMENTS SIGNALS, BELLS, GATES, SIGNS, MARKINGS AND LEDGENDS REF # 1305(XV-R) ON 22ND STREET AT CSX AT DOT # 352619R | 2020 | Exempt | 237105 | 26345 | 263450 | 2020-03-11
ALDOT | Delete Project | 100061165 | RHCH-RR13(909) | Safety | CN | PINE LANE/REF. # 1255(XIII-R)/DOT # 639 526U | 2020 | Exempt | 4555.8 | 506.2 | 5062 | 2020-03-11
ALDOT | Add New Project | 100071054 | STPAA-NR20(904) | Surface Transportation Program - Any Area | SP | REGIONAL TRANSPORTATION MANAGEMENT CENTER AND ASAP PROGRAM FROM FY2020-2021 | 2020 | Exempt | 1800000 | 200000 | 2000000 | 2020-03-11
Shelby County | Add New Project | 100070890 | BR-5914 | Bridge | CN | BRIDGE REPLACEMENT (BIN 015617) AND APPROACHES ON CR-24 OVER SPRING CREEK - SCP 59-810-12 | 2020 | Exempt | 680000 | 170000 | 850000 | 2020-03-11
Hoover | Increase CMAQ from $1,019,024 to $1,861,440 | 100056547 | CMAQ-3715(254) | Congestion Mitigation Air Quality (CMAQ) | CN | SIDEWALK ON VALLEY STREET, TYLER ROAD, CLOUDLAND DRIVE, SAVOY STREET AND CLEARVIEW ROAD IN BLUFF PARK GRADE, DRAIN, CURB AND GUTTER, AND SIDEWALK | 2020 | Exempt | 1861440 | 465360 | 2326800 | 2020-03-11
Vestavia Hills | Increase CMAQ from $72,753 to $359,071 | 100057172 | CMAQ-7030(600) | Congestion Mitigation Air Quality (CMAQ) | RW | SIDEWALKS ALONG CR-42 (MASSEY ROAD) FROM SR-3 (US-31, MONTGOMERY HIGHWAY) TO CR-99 (COLUMBIANA ROAD) IN VESTAVIA HILLS | 2020 | Exempt | 316000 | 79000 | 395000 | 2020-03-11
City of Birmingham | Delete phase | 100064292 | CMAQ-3715(262) | Congestion Mitigation Air Quality (CMAQ) | RW | STREETSCAPE IMPROVEMENTS ALONG 2ND AVE SOUTH FROM 24TH ST S TO 32ND ST S, 27TH ST S FROM 2ND AVE S TO 3RD AVE S, AND 29TH ST S FROM 2ND AVE S TO 3RD AVE S | 2020 | Exempt | 75200 | 18800 | 94000 | 2020-03-11
City of Birmingham | Delete phase | 100064563 | TAPBH-TA15(947) | TAP - Birmingham MPO | CN | COMPLETE STREET AND STORMWATER REMEDIATION ON SECOND AVENUE SOUTH IN THE LAKEVIEW NEIGHBORHOOD WITHIN THE CITY LIMITS OF BIRMINGHAM. | 2020 | Exempt | 400000 | 100000 | 500000 | 2020-03-11
Wilsonville | Add $78,613 of MPO TAP funds | 100067296 | TAPNU-TA(907) | $399,715 of TAP Any Area - $78,613 of MPO TAP | CN | STREETSCAPE IMPROVEMENTS FROM DOWNTOWN WILSONVILLE TO NEW COMMERCIAL DEVELOPMENT ON SR-25 | 2020 | Exempt | 478328 | 119582 | 597910 | 2020-03-11
ALDOT | Add New Project | 100064600 | RACR-037-I59-010-PE | State Funding | PE | RECONSTRUCTION AND LANE ADDITION ON I-59 FROM I-459 TO CR-10 (CHALKVILLE MOUNTAIN ROAD) | 2020 | Non-Exempt* | 0 | 500000 | 500000 | 2020-08-12
ALDOT | Add New Project | 100064602 | RACR-037-I59-010-CN | Inerstate Maintenance and State Funding | CN | RECONSTRUCTION AND LANE ADDITION ON I-59 FROM I-459 TO CR-10 (CHALKVILLE MOUNTAIN ROAD) | 2022 | Non-Exempt* | 10131678.9 | 12383163.1 | 22514842 | 2020-08-12
ALDOT | Add New Project | 100070153 | STPAA-0139() | Surface Transportation Program - Any Area | FM | RESURFACING, PLANING, STRIPING, LEVELING AND PATCHING ON SR-139 FROM THE BIBB COUNTY LINE TO SR-25 IN WILTON | 2020 | Exempt | 152723.2 | 38180.8 | 190904 | 2020-08-12
ALDOT | Add New Project | 100071626 | STPAA-3720() | Surface Transportation Program - Any Area | CN | RESURFACING ON MINOR PARKWAY FROM BIRMINGPORT ROAD (SR-269) TO CRUMLY CHAPEL ROAD | 2020 | Exempt | 1185768.8 | 296442.2 | 1482211 | 2020-08-12
ALDOT | Add New Project | 100071708 | STPAA-I065() | Surface Transportation Program - Any Area | CN | ITS MANAGEMENT WORK PROJECT TSMO ON I-65 FOR FY-2021 FOR CALERA, ALABASTER AND PELHAM | 2020 | Exempt | 1939200 | 484800 | 2424000 | 2020-08-12
ALDOT | Add New Project | 100071709 | STPAA-0003() | Surface Transportation Program - Any Area | CN | THE INSTALLATION OF ITS DEVICES AND NETWORK INFRASTRUCTURE TO SUPPORT ADVANCED CORRIDOR MANAGEMENT TSMO ON SR-3 (US-31) | 2020 | Exempt | 2088680 | 522170 | 2610850 | 2020-08-12
ALDOT | Add New Project | 100071710 | STPAA-0003() | Surface Transportation Program - Any Area | CN | THE INSTALLATION OF ITS DEVICES AND NETWORK INFRASTRUCTURE TO SUPPORT ADVANCED CORRIDOR MANAGEMENT (TSMO) FOR 313 SIGNALIZED INTERSECTIONS ALONG US-11, US-31, US-78 AND US-280 IN JEFFERSON AND SHELBY COUNTIES | 2020 | Exempt | 5118776.8 | 1279694.2 | 6398471 | 2020-08-12
ALDOT | Add New Project | 100069286 | IM-I059() | Inerstate Maintenance | CN | CONCRETE REHABILITATION, SHOULDER RECONSTRUCTION, BRIDGE RAIL RETROFIT, AND RAMP IMPROVEMENTS ON I-59 FROM JUST SOUTH OF CR-10 TO JUST PAST THE ST. CLAIR COUNTY LINE | 2020 | Exempt | 16496457.3 | 1832939.7 | 18329397 | 2020-08-12
ALDOT | Add New Project | 100069855 | IM-I059() | Inerstate Maintenance | PE | PAVEMENT PRESERVATION ON I-59 FROM THE PAVEMENT JOINT SOUTH OF ALABAMA ADVENTURE PKWY (EXIT 110) TO PAVEMENT JOINT SOUTH OF THE BRIDGES OVER FAIRFIELD BLVD (BINS 12318 AND 12319) | 2020 | Exempt | 225000 | 25000 | 250000 | 2020-08-12
ALDOT | Add New Project | 100069856 | IM-I059() | Inerstate Maintenance | CN | PAVEMENT PRESERVATION ON I-59 FROM THE PAVEMENT JOINT SOUTH OF ALABAMA ADVENTURE PKWY (EXIT 110) TO PAVEMENT JOINT SOUTH OF THE BRIDGES OVER FAIRFIELD BLVD (BINS 12318 AND 12319) | 2020 | Exempt | 5174378.1 | 574930.9 | 5749309 | 2020-08-12
ALDOT | Add New Project | 100071617 | IM-I020() | Inerstate Maintenance | CN | PLANING, OVERLAY AND STRIPING ON I-20 FROM THE EAST END OF THE BRIDGE OVER 1ST AVE. NORTH TO THE EAST END OF THE BRIDGE OVER US-78 (AL-4) AT EXIT 140 | 2020 | Exempt | 7611303.6 | 845700.4 | 8457004 | 2020-08-12
ALDOT | Add New Project | 100071621 | IM-I459() | Inerstate Maintenance | CN | PLANING, OVERLAY AND STRIPING ON I-459 FROM .25 MILES SOUTH OF US-280(AL-38) TO .24 MILES SOUTH OF GRANTS MILL ROAD | 2020 | Exempt | 5960394 | 662266 | 6622660 | 2020-08-12
ALDOT | Add New Project | 100072235 | RPTOC-TR20() | Transit | TR | SECTION 5311 APPA TRANSIT BHAM REG PARATRANSIT CONSORTSIUM (CLASTRAN) CAPITAL SUPPORT EQUIP FY2020 | 2020 | Exempt | 132902.5 | 132902.5 | 265805 | 2020-08-12
ALDOT | Add New Project | 100072236 | PDRPTO8-TR20() | Transit | TR | SECTION 5311 TRANSIT CARES ACT BHAM REG PARATRANSIT CONSORTIUM (CLAS TRAN) OPERATING FY 2020 | 2020 | Exempt | 120000 | 0 | 120000 | 2020-08-12
ALDOT | Add $33,494 CMAQ funding | 100068637 | STPAA-0004(546) | Congestion Mitigation Air Quality (CMAQ) | CN | RESURFACING, PLANING, STRIPING, LEVELING AND PATCHING ON SR-4 (US-78) FROM 1ST AVE NORTH TO A POINT 86 FEET WEST OF 46TH ALLEY SOUTH INCLUDING EASTBOUND AND WESTBOUND LANES | 2020 | Exempt | 33493.808 | 8373.452 | 41867.26 | 2020-08-12
ALDOT | Add $59,199 CMAQ funding | 100068636 | STPAA-0004(548) | Congestion Mitigation Air Quality (CMAQ) | CN | RESURFACING, PLANING, STRIPING, LEVELING AND PATCHING ON SR-4 (US-78) FROM A SPOT 86 FEET WEST OF 46TH ALLEY SOUTH TO ST. PATRICK CIRCLE | 2020 | Exempt | 59199.44 | 14799.86 | 73999.3 | 2020-08-12
ALDOT | Add $89,569 CMAQ funding | 100070151 | STPAA-HSIP-0003(620) | Congestion Mitigation Air Quality (CMAQ) | CN | RESURFACING, PLANING, STRIPING, LEVELING, PATCHING AND 2FT SAFETY WIDENING ON SR-3(US-31) FROM .2 MILE NORTH OF FINLEY BLVD TO A JOINT AT 52ND AVE NORTH | 2020 | Exempt | 89569.088 | 22392.272 | 111961.36 | 2020-08-12
Jefferson County | Move to FY2024 | 100056290 | STPBH-7021() | Surface Transportation Program - Birmingham | CN | CR-46 (HUEYTOWN ROAD) ADDITIONAL TURN LANES AND INTERSECTION IMPROVEMENTS FROM WALKER AVENUE TO NORTH OF HILLSIDE DRIVE | 2024 | Non-Exempt* | 1200000 | 300000 | 1500000 | 2020-08-12
Clastran | Add New Project | 100072432 | STPBH-TR21() | Surface Transportation Program - Birmingham | TR | FLEXIBLE FUNDS TRANSFER TO FTA FOR PARATRANSIT CONSORTIUM - ADDITIONAL FUNDING FOR FY2021 - OPERATIONS | 2021 | Exempt | 1000000 | 250000 | 1250000 | 2020-08-12
City of Mountain Brook | Add $236,509 CMAQ funding | 100064200 | CMAQ-3715() | Congestion Mitigation Air Quality (CMAQ) | RW | INTERSECTION IMPROVEMENTS CAHABA RD/SR-38(US-280)/CULVER RD/LANE PARK RD-CITY OF MOUNTAIN BROOK | 2020 | Exempt | 539200 | 134800 | 674000 | 2020-08-12
City of Alabaster | Add $400,000 CMAQ funding and modify description | 100032369 | CMAQ-9802() | Congestion Mitigation Air Quality (CMAQ) | CN | ADA UPGRADES AND IMPROVEMENTS TO BUCK CREEK MULTI-USE TRAIL FROM YMCA TO BUCK CREEK PARK: CITY OF ALABASTER . | 2023 | Exempt | 634766 | 158691.5 | 793457.5 | 2020-08-12
City of Alabaster | Add PE phase | 100072376 | CMAQ-9802() | Congestion Mitigation Air Quality (CMAQ) | PE | ADA UPGRADES AND IMPROVEMENTS TO BUCK CREEK MULTI-USE TRAIL FROM YMCA TO BUCK CREEK PARK: CITY OF ALABASTER . | 2020 | Exempt | 80000 | 20000 | 100000 | 2020-08-12
St. Clair County | Add New Project | 100071677 | CMAQ-0025() | Congestion Mitigation Air Quality (CMAQ) | UT | INTERSECTION IMPROVEMENTS ON SR-25 (US-411) AT CR-6(SANIE ROAD/SIMPSON ROAD) PHASE 2 | 2022 | Exempt | 122412 | 30603 | 153015 | 2020-08-12
St. Clair County | Add New Project | 100071679 | CMAQ-0025() | Congestion Mitigation Air Quality (CMAQ) | CN | INTERSECTION IMPROVEMENTS ON SR-25 (US-411) AT CR-6(SANIE ROAD/SIMPSON ROAD) PHASE 2 | 2022 | Exempt | 816080 | 204020 | 1020100 | 2020-08-12
City of Leeds | Delete Project | 100064310 | CMAQ-3715(271) | Congestion Mitigation Air Quality (CMAQ) | PE | INTERSECTION IMPROVEMENTS AT REX LAKE ROAD AND ZEIGLER ROAD | na | Exempt | 160000 | 40000 | 200000 | 2020-08-12
City of Leeds | Delete Project | 100064311 | CMAQ-3715(271) | Congestion Mitigation Air Quality (CMAQ) | RW | INTERSECTION IMPROVEMENTS AT REX LAKE ROAD AND ZEIGLER ROAD | na | Exempt | 160000 | 40000 | 200000 | 2020-08-12
City of Leeds | Add New Project | 100072379 | tbd | Congestion Mitigation Air Quality (CMAQ) | PE | INTERSECTION IMPROVEMENTS AND SIGNALIZATION AT THE I-20/US-78 INTERCHANGE (EXIT 140) IN CITY OF LEEDS | 2020 | Exempt | 80000 | 20000 | 100000 | 2020-08-12
City of Leeds | Add New Project | 100072380 | tbd | Congestion Mitigation Air Quality (CMAQ) | CN | INTERSECTION IMPROVEMENTS AND SIGNALIZATION AT THE I-20/US-78 INTERCHANGE (EXIT 140) IN CITY OF LEEDS | 2022 | Exempt | 320000 | 80000 | 400000 | 2020-08-12
Arc of Central Alabama | Add New 5310 Project | 100072381 | tbd | Transit 5310 funding | TR | Passenger Vans | 2020 | Exempt | 133563 | 33390.75 | 166953.75 | 2020-08-12
Arc of Shelby | Add New 5310 Project | 100072382 | tbd | Transit 5310 funding | TR | Passenger Van | 2020 | Exempt | 33440 | 8360 | 41800 | 2020-08-12
BJCTA | Add New 5310 Project | 100072383 | tbd | Transit 5310 funding | TR | Passenger CNG Cutaways | 2020 | Exempt | 479565 | 119891.25 | 599456.25 | 2020-08-12
Glenwood | Add New 5310 Project | 100072384 | tbd | Transit 5310 funding | TR | Passenger vehicles and Cameras | 2020 | Exempt | 404140 | 101035 | 505175 | 2020-08-12
Kid One | Add New 5310 Project | 100072385 | tbd | Transit 5310 funding | TR | Engine, Tires, & Misc Equipment | 2020 | Exempt | 21912 | 5478 | 27390 | 2020-08-12
Lakeshore Foundation | Add New 5310 Project | 100072386 | tbd | Transit 5310 funding | TR | Wheelchair accessible cart | 2020 | Exempt | 14080 | 3520 | 17600 | 2020-08-12
Lawson State Community College | Add New 5310 Project | 100074000 | tbd | Transit 5310 funding | TR | Radio System | 2020 | Exempt | 176 | 44 | 220 | 2020-08-12
Travelers Aid | Add New 5310 Project | 100072387 | tbd | Transit 5310 funding | TR | Passenger van and purchased trips | 2020 | Exempt | 142736 | 35684 | 178420 | 2020-08-12
Vestavia Hills Recreation Dept | Add New 5310 Project | 100072388 | tbd | Transit 5310 funding | TR | Passenger van, phone & camera | 2020 | Exempt | 66774 | 16693.5 | 83467.5 | 2020-08-12
Warrior Senior Center | Add New 5310 Project | 100072390 | tbd | Transit 5310 funding | TR | Passenger van | 2020 | Exempt | 57200 | 14300 | 71500 | 2020-08-12
RPCGB | Add New 5310 Project | 100072401 | tbd | Transit 5310 funding | TR | ADMINISTRATIVE COSTS FOR 5310 PROGRAM MANAGEMENT - FY2020 and 2021 | 2020 | Exempt | 110000 | 0 | 110000 | 2020-08-12
ALDOT | Move from FY2026 to FY2021 | 100048414 | ACNHF-1602-(542) | Appalachian Highway System | PE | BIRMINGHAM NORTHERN BELTLINE FROM SR-79 TO SR-75; INCLUDES RAMPS B AND D AT SR-79 AND RAMPS F, H, AND J AT SR-75. | 2021 | Non-Exempt* | 682252.8 | 170563.2 | 852816 | 2020-11-04
ALDOT | Add New Project | 100071994 | APDF-1602() | Appalachian Highway System | PE | BIRMINGHAM NORTHERN BELTLINE DUAL MAINLINE BRIDGES OVER SELF CREEK AT STATIONS 2183+00 TO 2199+00, DUAL MAINLINE BRIDGES AT STATIONS 2208+50 TO 2218+50, AND SINGLE RAMP BRIDGES ON RAMPS B AND D AT SR-79 | 2021 | Non-Exempt* | 2020000 | 505000 | 2525000 | 2020-11-04
ALDOT | Add New Project | 100071618 | IM-I459() | Interstate Maintenance | PE | PLANING, OVERLAY AND STRIPING ON I-459 FROM A JOINT SOUTH OF US-280(AL-38) TO A JOINT SOUTH OF GRANTS MILL ROAD | 2021 | Exempt | 272700 | 30300 | 303000 | 2020-11-04
ALDOT | Add New Project | 100071616 | IM-I020() | Interstate Maintenance | PE | PLANING, OVERLAY AND STRIPING ON I-20 FROM THE EAST END OF THE BRIDGE OVER 1ST AVE. NORTH TO THE EAST END OF THE BRIDGE OVER US-78 (AL-4) AT EXIT 140 | 2021 | Exempt | 363600 | 40400 | 404000 | 2020-11-04
ALDOT | Add New Project | 100071981 | STPAA-0075() | Surface Transportion Program Any Area | FM | STRIPING AND SURFACE TREATMENT ON SR-75 FROM THE JEFFERSON COUNTY LINE TO THE BRIDGE OVER BLACKBURN FORK RELIEF BRIDGE 0.15 MILE SOUTH OF CR-19 (REMLAP DRIVE) | 2021 | Exempt | 2732108.4 | 303567.6 | 3035676 | 2020-11-04
ALDOT | Add New Project | 100070165 | NH-0038 | National Highway System | FM | RESURFACING, PLANING, STRIPING, LEVELING AND PATCHING ON SR-38 (US-280) FROM 422 FT EAST OF HUGH DANIEL DRIVE TO 317 FT EAST OF NARROWS PARKWAY | 2021 | Exempt | 2421139.5 | 269015.5 | 2690155 | 2020-11-04
ALDOT | Add New Project | 100071977 | NH-0003 | National Highway System | FM | RESURFACING, PLANING, STRIPING AND PATCHING ON SR-3 (US-31) FROM HOLLYWOOD BLVD TO UNIVERSITY BLVD | 2021 | Exempt | 2522988.9 | 280332.1 | 2803321 | 2020-11-04
ALDOT | Add New Project | 100071978 | STPAA-0007() | Surface Transportion Program Any Area | FM | STRIPING AND SURFACE TREATMENT ON SR-7 (US-11) FROM 236 FT SOUTH OF CHEROKEE DRIVE ON THE SOUTH END OF CAHABA RIVER BRIDGE TO THE ST. CLAIR COUNTY LINE | 2021 | Exempt | 1095840 | 121760 | 1217600 | 2020-11-04
Homewood | Add $3,676,669 of STPBH | 100029563 | STPBH-9802() | Surface Transportion Program Birmingham Attributable | RW | ADDITIONAL LANES ON OXMOOR BOULEVARD FROM SUMMIT PARKWAY TO COLUMBIANA ROAD | 2021 | Non-Exempt* | 3920000 | 980000 | 4900000 | 2020-11-04
Homewood | Move to FY2024 | 100029566 | STPBH-9802() | Surface Transportion Program Birmingham Attributable | UT | ADDITIONAL LANES ON OXMOOR BOULEVARD FROM SUMMIT PARKWAY TO COLUMBIANA ROAD | 2024 | Non-Exempt* | 697566 | 174391.5 | 871957.5 | 2020-11-04
Homewood | Move to FY2024 | 100029510 | STPBH-9802() | Surface Transportion Program Birmingham Attributable | CN | ADDITIONAL LANES ON OXMOOR BOULEVARD FROM SUMMIT PARKWAY TO COLUMBIANA ROAD | 2024 | Non-Exempt* | 3597000.8 | 899250.2 | 4496251 | 2020-11-04
Bessemer | Delete | 100064228 | CMAQ-3715(270) | Congestion Mitigation Air Quality | RW | PEDESTRIAN BRIDGE OVER SR-150 BETWEEN BERKLEY AVE AND CLARENDON AVE - CITY OF BESSEMER | - | Exempt | 85770.4 | 21442.6 | 107213 | 2020-11-04
Bessemer | Move to FY2021 and add $800,378 CMAQ funding | 100064230 | CMAQ-3715(270) | Congestion Mitigation Air Quality | CN | PEDESTRIAN BRIDGE OVER SR-150 BETWEEN BERKLEY AVE AND CLARENDON AVE - CITY OF BESSEMER | 2021 | Exempt | 1675326.4 | 418831.6 | 2094158 | 2020-11-04
Vestavia Hills | Add $1,087,955 CMAQ funding | 100051157 | HPP-TAPBH-CMAQ-A104(916) | High Priority, Transporation Alternative, and Congestion Mitigation Air Quality | CN | PEDESTRIAN BRIDGE OVER US-31 AND SIDEWALKS IN VESTAVIA HILLS NEAR WALD PARK | 2021 | Exempt | 2151899.2 | 537974.8 | 2689874 | 2020-11-04
Trussville | Move to FY2024 | 100052630 | CMAQ-9802() | Congestion Mitigation Air Quality | CN | TRUSSVILLE GREENWAY AND WALKWAY MULTI-USE TRAIL-GREENWAY FROM CHALKVILLE MTN RD (CR-10) TO CALUMET PARKWAY NEAR SR-7 (US-11) (PHASE 1) | 2024 | Exempt | 1185714.4 | 296428.6 | 1482143 | 2020-11-04
Springville | Add New Project | 100072217 | ATRP2-58-2020-462-RW | ATRIP2 | RW | INTERSECTION IMPROVEMENTS AT SR-7 (US-11) SR-174 AND CR-9; INCLUDING A TRAFFIC SIGNAL AND TURN LANES ON ALL FOUR APPROACHES | 2021 | Exempt | 0 | 50000 | 50000 | 2020-11-04
Springville | Add New Project | 100071099 | ATRP2-58-2020-462-CN | ATRIP2 | CN | INTERSECTION IMPROVEMENTS AT SR-7 (US-11) SR-174 AND CR-9; INCLUDING A TRAFFIC SIGNAL AND TURN LANES ON ALL FOUR APPROACHES | 2021 | Exempt | 0 | 1950000 | 1950000 | 2020-11-04
Springville | Delete | 100070045 | CMAQ-0174() | Congestion Mitigation Air Quality | PE | INTERSECTION IMPROVEMENTS AT SR-174, MURPHREES VALLEY ROAD AND SR-7 (US-11) | - | Exempt | 624301.6 | 156075.4 | 780377 | 2020-11-04
Springville | Delete | 100070048 | CMAQ-0174() | Congestion Mitigation Air Quality | RW | INTERSECTION IMPROVEMENTS AT SR-174, MURPHREES VALLEY ROAD AND SR-7 (US-11) | - | Exempt | 83248 | 20812 | 104060 | 2020-11-04
Shelby County | Add $826,150 CMAQ funding | 100054519 | CMAQ-5917(904) | Congestion Mitigation Air Quality | CN | INVERNESS COMMUNITY GREENWAY FROM INVERNESS FIRE STATION TO HOOVER'S NATURE PARK | 2020 | Exempt | 1868396.8 | 467099.2 | 2335496 | 2020-11-04 | #REF! | #REF!
Midfield | Delete | 100065504 | TAPAA-CMAQ TA14 (930) | Congestion Mitigation Air Quality | UT | DOWNTOWN STREETSCAPE AND SIDEWALKS ALONG B.Y. WILLIAMS SR. DRIVE IN THE CITY OF MIDFIELD | - | Exempt | 82424 | 20606 | 103030 | 2020-11-04
Adamsville | Delete | 100048382 | STPBH-7234(600) | Surface Transportion Program Birmingham Attributable | CN | SIDEWALKS ALONG CR-67 (HAZELWOOD ROAD) FROM BURGANDY DR TO HARRIS AVENUE | - | Exempt | 85633.6 | 21408.4 | 107042 | 2020-11-04
Vincent | Add $60,000 of MPO TAP funding | 100064513 | TAPAA-TA15(909) | Transportation Alternative Program MPO | CN | SIDEWALK IMPROVEMENTS ALONG SR-25 (231) FROM EMBRY DR TO CR-83 AND ALONG FLOREY ST FROM SR-25 (US-231) BETWEEN THE TWO EAST HIGHLAND DRIVES | 2019 | Exempt | 565000 | 141250 | 706250 | 2020-11-04
Birmingham | Add UT phase | 100072431 | CMAQ-3718() | Congestion Mitigation Air Quality | UT | GREENWAY AND ROAD DIET ON RICHARD ARRINGTON JR BOULEVARD FROM 15TH AVENUE SOUTH TO VALLEY AVENUE | 2023 | Exempt | 16484.8 | 4121.2 | 20606 | 2020-11-04
Birmingham | Add RW phase | 100072764 | STPBH-7117(600) | Surface Transportion Program Birmingham Attributable | RW | STREETSCAPE AND TRANSPORTATION ON 16TH STREET CORRIDOR FROM 11TH AVE NORTH TO I-65 WITHIN FOUNTAIN HEIGHTS NEIGHBORHOOD | 2021 | Exempt | 100000 | 25000 | 125000 | 2020-11-04
Bessemer | Add New Project | 100072765 | TAPBH-TA21() | Transportation Alternative Program MPO | CN | STREETSCAPE IMPROVEMENTS ALONG 19TH STREET NORTH FROM 1ST TO 4TH AVENUE NORTH | 2022 | Exempt | 640000 | 160000 | 800000 | 2020-11-04
Irondale | Add New Project | 100072766 | TAPBH-TA21() | Transportation Alternative Program MPO | CN | SIDEWALKS ON 16TH ST, 2ND AVE, 5TH AVE, AND 20TH ST | 2022 | Exempt | 640000 | 160000 | 800000 | 2020-11-04
Birmingham | Delete | 100064283 | CMAQ-3715(267) | Congestion Mitigation Air Quality | PE | VULCAN TRAIL EXTENSION FROM 11TH PLACE SOUTH TO GREEN SPRINGS HIGHWAY | - | Exempt | 60000 | 15000 | 75000 | 2021-02-10
Birmingham | Delete | 100064288 | CMAQ-3715(267) | Congestion Mitigation Air Quality | RW | VULCAN TRAIL EXTENSION FROM 11TH PLACE SOUTH TO GREEN SPRINGS HIGHWAY | - | Exempt | 40000 | 10000 | 50000 | 2021-02-10
Birmingham | Delete | 100064289 | CMAQ-3715(267) | Congestion Mitigation Air Quality | UT | VULCAN TRAIL EXTENSION FROM 11TH PLACE SOUTH TO GREEN SPRINGS HIGHWAY | - | Exempt | 40000 | 10000 | 50000 | 2021-02-10
Birmingham | Delete | 100064290 | CMAQ-3715(267) | Congestion Mitigation Air Quality | CN | VULCAN TRAIL EXTENSION FROM 11TH PLACE SOUTH TO GREEN SPRINGS HIGHWAY | - | Exempt | 320000 | 80000 | 400000 | 2021-02-10
Birmingham | Delete | 100066621 | CMAQ-3717() | Congestion Mitigation Air Quality | PE | BIKESHARE WAYFINDING SIGNS IN DOWNTOWN BIRMINGHAM | - | Exempt | 186400 | 46600 | 233000 | 2021-02-10
Birmingham | Delete | 100066622 | CMAQ-3717() | Congestion Mitigation Air Quality | CN | BIKESHARE WAYFINDING SIGNS IN DOWNTOWN BIRMINGHAM | - | Exempt | 1165804 | 291451 | 1457255 | 2021-02-10
ALDOT | Modify Description and add $1,812,204 of CMAQ funding | 100064507 | CMAQ-0003() | Congestion Mitigation Air Quality | CN | AUXILIARY LANES ON SR-3(US-31/RED MOUNTAIN EXPRESSWAY) BETWEEN HIGHLAND AVE AND 21ST AVE. AND IMPROVEMENTS TO NORTHBOUND EXIT RAMP AT UNIVERSITY BLVD. INTERCHANGE | 2021 | Exempt | 4519346 | 1129836.5 | 5649182.5 | 2021-02-10
ALDOT | Add New Project | 100072848 | STPAA-I065() | Surface Transportion Program Any Area | PE | THE INSTALLATION OF ITS INFRASTRUCTURE (COMMUNICATIONS, DETECTION, SURVEILLANCE, AND MESSAGING) TSMO ON I-65 AND SR-3/US-31 TO SUPPORT THE ADVANCED FREEWAY TRAFFIC MANAGEMENT SUBSYSTEM COMPONENT OF THE I-65/US-31 ADVANCED CORRIDOR MANAGEMENT SYSTEM | 2021 | Exempt | 400000 | 100000 | 500000 | 2021-02-10
ALDOT | Move from FY2024 to FY2022 | 100064120 | NH-I059() | National Highway System | PE | I-59 ADD LANES FROM SR-7 (US-11 1ST AVENUE NORTH) TO NORTH OF SR-75 (ROEBUCK PARKWAY) | 2022 | Non-Exempt* | 1715416.8 | 428854.2 | 2144271 | 2021-02-10
ALDOT/ Fultondale | Add $174,327 of STPBH funding | 100062542 | STPBH-I065(475) | Surface Transportion Program Birmingham Attributable | CN | INTERSTATE LIGHTING UPGRADE ON I-65 FROM 0.7 MILES NORTH OF CR-120 (WALKER CHAPEL ROAD) EXIT 267 TO 0.25 MILES NORTH OF RIDGEBROOK ROAD JEFFERSON COUNTY | 2018 | Exempt | 746817.6 | 186704.4 | 933522 | 2021-02-10
Hoover | Delete | 100068449 | TAPBH-TA18(932) | MPO Transportation Alternative Program | CN | SIDEWALK LANDSCAPING AND LIGHTING AROUND THE HOOVER PUBLIC LIBRARY CORNER LOT BETWEEN MUNICIPAL LANE MONTGOMERY HIGHWAY AND MUNICIPAL DRIVE | - | Exempt | 583022 | 145755.5 | 728777.5 | 2020-02-10
Midfield | Add $124,277 of MPO TAP funding | 100065517 | TAPAA-TA16(900) | MPO and ALDOT Transportation Alternative Program | CN | SIDEWALKS ON GRANT ST FROM BRELAND DR TO BRIZENDINE DR ON BRIZENDINE DR FROM GRANT ST TO ELAM ST ON ELAM ST FROM BRIZENDINE DR TO BRYSON ST ON BRYSON ST FROM ELAM ST TO LOVOY ST ON LOVOY ST NORTH TO THE INTERSECTION OF SHORT ST AND BY WILLIAMS SR | 2019 | Exempt | 524137.6 | 131034.4 | 655172 | 2021-02-10
Trussville | Add $792,102 of STPBH funding | 100039839 | STPBH-7073(602) | Surface Transportion Program Birmingham Attributable | CN | WIDEN SR-7(US-11) FROM CHALKVILLE RD TO THE CAHABA RIVER BRIDGE | 2021 | Non-Exempt* | 2841552 | 710388 | 3551940 | 2021-02-10
Bessemer | Add New Project | 100071226 | RALG-37-2020-107 | Rebuild Alabama | CN | BRIDGE REPAIR AND REMEDIATION OF AVE I BRIDGE (BIN 010094) OVER SR-150 | 2021 | Exempt | 0 | 250000 | 250000 | 2021-02-10
St. Clair County | Add New Project | 100071412 | RALG-58-2020-058 | Rebuild Alabama | CN | RESURFACING ON CR-9 FROM SR-7 (US-11) TO THE BLOUNT COUNTY LINE AND ON 19TH STREET FROM SR-53 (US-231) TO THE NORFOLK SOUTHERN RAILROAD | 2021 | Exempt | 0 | 250000 | 250000 | 2021-02-10
Vincent | Add New Project | 100071221 | RALG-59-2020-503 | Rebuild Alabama | CN | RESURFACING 17 SITES IN THE TOWN OF VINCENT | 2021 | Exempt | 0 | 250000 | 250000 | 2021-02-10
Fairfield | Add New Project | 100071198 | RALG-37-2020-203 | Rebuild Alabama | CN | RESURFACING E. J. OLIVER BLVD, (1.0 MILES) E. J. OLIVER BLVD BEGINS AT AARON ARONOV DR. (64TH ST.) AND ENDS AT VALLEY ROAD | 2021 | Exempt | 0 | 250000 | 250000 | 2021-02-10
Calera | Add New Project | 100071235 | RALG-59-2020-126 | Rebuild Alabama | CN | RESURFACING ON GEORGE ROY PARKWAY FROM CR-22 TO CR-87 | 2021 | Exempt | 0 | 250000 | 250000 | 2021-02-10
Kid One | Add New Project | 100072743 | NFIGR-TR21() | Transit | TR | SECTION 5317 TRANSIT (RURAL) KID ONE TRANSPORT SYSTEM, INC. (OPERATING) FY 2021 | 2021 | Exempt | 216000 | 54000 | 270000 | 2021-02-10
RPCGB | Add New Project | 100073252 | TBD | Congestion Mitigation Air Quality | SP | OZONE AWARENESS PROGRAM FY2022-2023 | 2022 | Exempt | 780000 | 195000 | 975000 | 2021-02-10
RPCGB | Add New Project | 100073253 | STPBH-NR21() | Surface Transportion Program Birmingham Attributable | SP | CORRIDOR FEASIBILITY STUDY OR APPLE PROGRAM FY2022-2023 | 2022 | Exempt | 640000 | 160000 | 800000 | 2021-02-10
RPCGB | Add New Project | 100073254 | STPBH-NR21() | Surface Transportion Program Birmingham Attributable | SP | TRANSPORTATION SYSTEMS MONITORING FOR CONGESTION MANAGEMENT SYSTEM (CMS) FY2022-2023 | 2022 | Exempt | 460800 | 115200 | 576000 | 2021-02-10
RPCGB | Add New Project | 100073255 | STPBH-NR21() | Surface Transportion Program Birmingham Attributable | SP | BUILDING COMMUNITIES PROGRAMS FY2022-2023 | 2022 | Exempt | 1600000 | 400000 | 2000000 | 2021-02-10
Jefferson County | Add New Project | 100073257 | STPBH-NR21() | Surface Transportion Program Birmingham Attributable | SP | JEFFERSON COUNTY COMPREHENSIVE PLAN | 2021 | Exempt | 250000 | 62500 | 312500 | 2021-02-10
Birmingham | Modify Description | 100069322 | FTA3-TR19() | Congestion Mitigation Air Quality | TR | BIRMINGHAM BRT - BUY EXPANSION BUSES - STD 40FT | 2021 | Exempt | 1504398.4 | 376099.6 | 1880498 | 2021-02-10
ALDOT | Add new project | 100073472 | RHPD-RR21 | Rail Road Safety Funds | CN | RR XING HAZARD ELIMINATION (INSTALL RAISED MEDIAN SEPARATOR WITH DELINEATORS ON APPROACHES) NORFOLK SOUTHERN RR IN JEFFERSON, CALHOUN, TUSCALOOSA, MADISON COUNTIES; REF # 2101HE, DOT #'S 728033C, 726013J, 727093H, 727089T, 728003K, 728030G, 731805N | 2021 | Exempt | 77304 | 19326 | 96630 | 2021-05-12
ALDOT | Add new project | 100073369 | 99-603-371-038-101 | State Funds | CN | INSTALLATION OF WIRELESS REDUNDANCY SYSTEM FOR ADAPTIVE TRAFFIC SIGNALS FROM OFFICE PARK TO DOUG BAKER BLVD | 2021 | Exempt | - | 200000 | 200000 | 2021-05-12
ALDOT | Add new project | 100071724 | IM-I459() | Interstate Maintenance | PE | PLANING, OVERLAY AND TRAFFIC STRIPE FROM MP 27.132 ON GRANTS MILL ROAD TO THE CONCRETE PAVEMENT AT MP 32.470 ON SR-7 (US-11) | 2022 | Exempt | 181800 | 20200 | 202000 | 2021-05-12
ALDOT | Add new project | 100073339 | IM-I065() | Interstate Maintenance | PE | PLANING, OVERLAY AND STRIPING ON I-65 FROM THE CHILTON COUNTY LINE TO THE NORTH END OF THE BRIDGE OVER CR-263 AND CSX RAILROAD (MP 237.530) | 2021 | Exempt | 887862.6 | 98651.4 | 986514 | 2021-05-12
ALDOT | Add new project | 100073340 | IM-I065() | Interstate Maintenance | CN | PLANING, OVERLAY AND STRIPING ON I-65 FROM THE CHILTON COUNTY LINE TO THE NORTH END OF THE BRIDGE OVER CR-263 AND CSX RAILROAD (MP 237.530) | 2022 | Exempt | 8967415.5 | 996379.5 | 9963795 | 2021-05-12
ALDOT | Add new project | 100073341 | IM-I459() | Interstate Maintenance | PE | CONCRETE PAVEMENT REHABILITATION ON I-459 FROM LORNA ROAD (MP 14.794) TO WEST OF SHADES CREEK | 2021 | Exempt | 2520000 | 280000 | 2800000 | 2021-05-12
ALDOT | Add new project | 100073344 | IM-I459() | Interstate Maintenance | CN | CONCRETE PAVEMENT REHABILITATION ON I-459 FROM LORNA ROAD (MP 14.794) TO WEST OF SHADES CREEK | 2023 | Exempt | 25706520 | 2856280 | 28562800 | 2021-05-12
ALDOT | Add new project | 100072710 | HRRR-0521 | Safety - High Risk Rural Roads | CN | RESURFACING AND WIDENING ON CR-8 (SKYLINE DRIVE) FROM RICKWOOD CAVERNS ROAD EASTERLY FOR 2.140 MILES (MP 4.355) | 2021 | Exempt | 290018.7 | 32224.3 | 322243 | 2021-05-12
ALDOT | Move from FY2023 to FY2024 | 100003396 | BR-0079(500) | Bridge Funds | CN | REPL BIN 004658, SR-79 OVER BLACKBURN FORK OF LITTLE WARRIOR RIVER (SUFF=44.7, STAT=SD) | 2024 | Exempt | 8418297.6 | 2104574.4 | 10522872 | 2021-05-12
ALDOT | Move from FY2023 to FY2024 | 100069530 | BR-0269() | Bridge Funds | CN | BRIDGE REPLACEMENT (BIN 009187) ON SR-269 (BIRMINGPORT ROAD) OVER THE LOCUST FORK OF THE WARRIOR RIVER | 2024 | Exempt | 7812788 | 1953197 | 9765985 | 2021-05-12
Vestavia Hills | Add $160,000 of MPO TAP funding | 100062997 | TAPAA-TA14(931) | MPO and ALDOT Transportation Alternative Program | CN | SICARD HOLLOW ROAD TUNNEL SAFE ROUTE FOR NON-DRIVERS. THIS PROJECT IS LOCATED AT A TUNNEL TO BE CONSTRUCTED UNDER SICARD HOLLOW ROAD IN LIBERTY PARK | 2017 | Exempt | 738966.4 | 184741.6 | 923708 | 2021-05-12
Montevallo | Add New Project | 100072684 | TAPAA-TA21(924) | Transportation Alternative Program - Any Area | CN | SIDEWALKS ALONG SR-25 IN THE CITY OF MONTEVALLO | 2021 | Exempt | 547900 | 136975 | 684875 | 2021-05-12
Hueytown | Add New Project | 100072661 | TAPOA-TA21(902) | Transportation Alternative Program - Any Area | CN | SIDEWALKS ON FOREST ROAD, FAIRLAWN DRIVE, CAMBRIDGE ROAD, PARSONS DRIVE, 22ND STREET AND SUNRISE BOULEVARD; ALSO A SIDEWALK ON FOREST ROAD CONNECTING TO 21ST STREET | 2021 | Exempt | 622478.4 | 155619.6 | 778098 | 2021-05-12
Center Point | Add $1,123,241 of STPBH funding | 100054521 | STPBH-3716(250) | Surface Transportion Program Birmingham Attributable | CN | RESURFACING, SIDEWALK ADDITIONS AND DRAINAGE IMPROVEMENTS ALONG POLLY REED ROAD FROM SR-75 TO REED ROAD NE | 2021 | Exempt | 4704000 | 1176000 | 5880000 | 2021-05-12
UAB | Move from FY2023 to FY2024 | 100068129 | CMAQ-3718() | Congestion Mitigation Air Quality | CN | ADD BIKE LANES AND STREETSCAPE IMPROVEMENTS ALONG 13TH STREET SOUTH FROM 4TH AVE SOUTH TO 10TH AVE SOUTH | 2024 | Exempt | 1748880.72 | 437220.18 | 2186100.9 | 2021-05-12
RPCGB | Add New Project | 100073605 | tbd | Surface Transportation Birmingham Attributable - CRRSSA Funds | SP | TECHNICAL ASSISTANCE SAFETY PROJECT PLANNING - FY2021-2023 | 2021 | Exempt | 300000 | - | 300000 | 2021-05-12
RPCGB | Add New Project | 100073606 | tbd | Surface Transportation Birmingham Attributable - CRRSSA Funds | SP | DISTRACTED DRIVING OUTREACH AND EDUCATION - UAB TRIP LAB - FY2021-2023 | 2021 | Exempt | 225000 | - | 225000 | 2021-05-12
Birmingham | Move from FY2024 to FY2022 | 100072429 | CMAQ-3718() | Congestion Mitigation Air Quality | CN | GREENWAY AND ROAD DIET ON RICHARD ARRINGTON JR BOULEVARD FROM 15TH AVENUE SOUTH TO VALLEY AVENUE | 2022 | Exempt | 1969663.2 | 492415.8 | 2462079 | 2021-05-12
ALDOT | Add new project | 100073601 | RHPD-RR21() | Rail Road Safety Funds | CN | RAILROAD CROSSING IMPROVEMENT, SIGNALS AND REPLACING CANTILEVER AT 31ST STREET AND NORFOLK SOUTHERN RAILWAY, DOT NO. 725384R | 2021 | Exempt | 360000 | 90000 | 450000 | 2021-08-11
ALDOT | Add new project | 100073602 | RHPD-RR21() | Rail Road Safety Funds | CN | RAILROAD CROSSING IMPROVEMENT, SIGNALS, MARKINGS, LEGENDS AND SIGNS AT 24TH STREET SOUTHWEST AND NORFOLK SOUTHERN RAILWAY, DOT NO. 725383J | 2021 | Exempt | 8000 | 2000 | 10000 | 2021-08-11
ALDOT | Add new project | 100073587 | RHPD-RR21() | Rail Road Safety Funds | CN | RAILROAD CROSSING IMPROVEMENTS, SIGNALS, GATES BELLS, LEGENDS AND MARKINGS AT CR-44 (1ST AVENUE WEST) AND CSX RAILROAD DOT NO. 352263K | 2021 | Exempt | 280000 | 70000 | 350000 | 2021-08-11
ALDOT | Add new project | 100073588 | RHPD-RR21() | Rail Road Safety Funds | CN | RAILROAD CROSSING IMPROVEMENTS, SIGNALS, BELLS, GATES, SIGNS, LEGENDS AND MARKINGS AT 6TH AVENUE SOUTHWEST AND CSX RAILROAD, DOT NO. 352264S | 2021 | Exempt | 280000 | 70000 | 350000 | 2021-08-11
ALDOT | Add new project | 100073572 | RHPD-RR21() | Rail Road Safety Funds | CN | RAILROAD CROSSING IMPROVEMENT, LEGENDS AND MARKINGS AND STOP BAR AT GRANT STREET AND NORFOLK SOUTHERN RAILWAY, DOT # 725407V | 2021 | Exempt | 8000 | 2000 | 10000 | 2021-08-11
ALDOT | Add new project | 100073515 | RHPD-RR21() | Rail Road Safety Funds | CN | RAILROAD CROSSING IMPROVEMENTS, GATES, SIGNS, LEGENDS AND MARKINGS AT SR-261 (HELENA ROAD) AND CSX RAILROAD, DOT NO. 639543K | 2021 | Exempt | 56000 | 14000 | 70000 | 2021-08-11
ALDOT | Add new project | 100073516 | RHPD-RR21() | Rail Road Safety Funds | CN | RAILROAD CROSSING IMPROVEMENTS, SIGNALS, GATES, BELLS, CONCRETE PANELS, SIGNS, LEGENDS AND MARKINGS AT CR-51 AND CSX RAILROAD, DOT NO 639416J | 2021 | Exempt | 400800 | 100200 | 501000 | 2021-08-11
ALDOT | Delete Project | 100064507 | CMAQ-0003() | Congestion Mitigation Air Quality | CN | AUXILIARY LANES ON SR-3(US-31/RED MOUNTAIN EXPRESSWAY) BETWEEN HIGHLAND AVE AND 21ST AVE. AND IMPROVEMENTS TO NORTHBOUND EXIT RAMP AT UNIVERSITY BLVD. INTERCHANGE | 2021 | Exempt | 4519346 | 1129836.5 | 5649182.5 | 2021-08-11
ALDOT | Add $4,519,346 of CMAQ funds and modify description | 100071977 | NH-CMAQ 0003 (630) | National Highway System and Congestion Mitigation Air Quality | FM | RESURFACING AUXILIARY LANES RAMP IMPROVEMENTS MEDIAN BARRIER RAIL AND BRIDGE RAIL RETROFITS ON SR-3 (US-31) FROM BONITA DRIVE TO 2ND AVE SOUTH | 2021 | Exempt | 7607253.15 | 845250.35 | 8452503.5 | 2021-08-11
Birmingham | Add new project | 100073285 | ATRP2-37-2021-109 | ATRIP2 | CN | RESURFACING AUXILIARY LANES RAMP IMPROVEMENTS MEDIAN BARRIER RAIL AND BRIDGE RAIL RETROFITS ON SR-3 (US-31) FROM BONITA DRIVE TO 2ND AVE SOUTH | 2021 | Exempt | - | 2000000 | 2000000 | 2021-08-11
ALDOT | Add new project | 100073896 | CRSA-NR21() | CRRSAA Funds | SP | ENHANCEMENTS AND IMPROVEMENTS TO THE SURFACE TRANSPORTATION ITS NETWORK | 2021 | Exempt | 1500000 | - | 1500000 | 2021-08-11
RPCGB | Add New Project | 100074088 | tbd | FTA 5310 | SP | Capital purchases for 5310 projects | 2022 | Exempt | 790000 | 0 | 790000 | 2021-08-11
RPCGB | Add New Project | 100074086 | tbd | CRRSAA Funds | SP | Operational expenses for 5310 projects | 2022 | Exempt | 125366 | 0 | 125366 | 2021-08-11
ClasTran | Add New Project | 100074087 | tbd | Surface Transportion Program Birmingham Attributable | SP | FLEXIBLE FUNDS TRANSFER TO FTA FOR PARATRANSIT CONSORTIUM - PURCHASED TRANSPORTATION | 2022 | Exempt | 1000000 | 250000 | 1250000 | 2021-08-11
ALDOT | Add new project | 100073398 | IM-I065() | Interstate Maintenance | PE | CONCRETE PAVEMENT REHAB, RESURFACING AND GUARDRAIL RESET ON I-65 FROM 16TH STREET NORTH OVERPASS TO DANIEL PAYNE DRIVE. | 2023 | Exempt | 240990.3 | 26776.7 | 267767 | 2021-08-11
ALDOT | Add new project | 100073403 | IM-I065() | Interstate Maintenance | CN | CONCRETE PAVEMENT REHAB, RESURFACING AND GUARDRAIL RESET ON I-65 FROM 16TH STREET NORTH OVERPASS TO DANIEL PAYNE DRIVE. | 2023 | Exempt | 2434005.9 | 270445.1 | 2704451 | 2021-08-11
Midfield | Delete Project | 100068363 | TAPAA-TA18(912) | Transportation Alternative Program - Any Area | CN | SIDEWALKS ALONG ALDEN AVENUE FROM 8TH STREET TO 12TH STREET AND ALONG 12TH STREET FROM ALDEN AVENUE TO 12TH AVENUE | 2021 | Exempt | 405245.6 | 101311.4 | 506557 | 2021-08-11
RPCGB | Add $600,000 of CMAQ funding from previous year | 100073252 | CMAQ-NR21() | Congestion Mitigation Air Quality | SP | OZONE AWARENESS PROGRAM FY 2022 - FY 2023 | 2022 | Exempt | 1380000 | 345000 | 1725000 | 2021-08-11
Bessemer | Add $554,936 CMAQ funding | 100064230 | CMAQ-3715(270) | Congestion Mitigation Air Quality | CN | PEDESTRIAN BRIDGE OVER SR-150 BETWEEN BERKLEY AVE AND CLARENDON AVE - CITY OF BESSEMER | 2022 | Exempt | 2230262.4 | 557565.6 | 2787828 | 2021-08-11
ALDOT | Add RW phase and split funding; $6,500,000 CRRSSA, $3,688,000 STPAA, & $922,000 local | 100074113 | STPAA-7112() | CRRSAA and STPAA | RW | ADDITIONAL LANES ON SR-261 FROM BEARDEN ROAD TO SR-3 (US-31) | 2022 | Non-Exempt* | 10188000 | 0 | 11110000 | 2021-12-08
ALDOT | Add $7,098,428 STPBH (remaining $14,604,972 is STPAA funding) | 100009265 | STPAA-7112() | STPAA and STPBH | CN | ADDITIONAL LANES ON SR-261 FROM BEARDEN ROAD TO SR-3 (US-31) | 2023 | Non-Exempt* | 21703400 | 5425850 | 27129250 | 2021-12-08
Hoover/Shelby County | Move to FY2024 | 100033064 | STPBH-9802(905) | Surface Transportion Program Birmingham Attributable(STPBH) | CN | VALLEYDALE RD FROM CALDWELL MILL RD TO MEADOW DRIVE - PHASE 1 | 2024 | Non-Exempt* | 16400000 | 4100000 | 20500000 | 2021-12-08
ALDOT | Add new project | 100074168 | ST-037-I59-013 | State Funds | PE | REPAIR AND REPLACEMENTS OF ENTRANCE AND EXIT RAMPS ON I-59/20 AT MCASHAN DRIVE | 2022 | Exempt | 0 | 300000 | 300000 | 2021-12-08
ALDOT | Add new project | 100074133 | STPAA-NR22() | Surface Transportion Program Any Area | SP | REGIONAL TRANSPORTATION MANAGEMENT CENTER AND ASAP PROGRAM FOR FY-2022 | 2022 | Exempt | 2400000 | 600000 | 3000000 | 2021-12-08
Mountain Brook | Increase from $250,000 to $464,236 total | 100066110 | STPBH-3716(256) | Surface Transportion Program Birmingham Attributable(STPBH) | PE | BRIDGE REPLACEMENT (BIN #012869) ON OLD BROOK TRAIL OVER LITTLE SHADES CREEK AND BRIDGE REHABILITATION (BIN #002873) ON CANTERBURY ROAD OVER WATKINS CREEK | 2017 | Exempt | 371388.8 | 92847.2 | 464236 | 2021-12-08
Alabaster | Add new project | 100074590 | TBD | Surface Transportion Program Birmingham Attributable(STPBH) | RW | ADDITIONAL LANES ON SR-119 FROM CR-80 TO CR-12 - PHASE 2 | 2022 | Non-Exempt* | 1200000 | 300000 | 1500000 | 2021-12-08
Center Point | Add new project | 100074604 | TBD | MPO Transportation Alternative Program (TAP) | CN | Center Point Community Center to Erwin Intermediate School - City of Center Point | 2022 | Exempt | 640000 | 160000 | 800000 | 2021-12-08
Alabaster | Add new project | 100074605 | TBD | MPO Transportation Alternative Program (TAP) | CN | Thompson Middle School to Thompson High School - City of Alabaster | 2022 | Exempt | 640000 | 160000 | 800000 | 2021-12-08
Homewood | Delete Project | 100065220 | CMAQ-TA15(903) | Congestion Mitigation Air Quality | UT | 18TH STREET REVITALIZATION FROM 28TH AVENUE SOUTH TO A POINT APPROXIMATELY 1000' NORTH OF ROSEDALE DRIVE IN THE CITY OF HOMEWOOD | 2021 | Exempt | 84922 | 21230.5 | 106152.5 | 2021-12-08
ALDOT | Add new project | 100073843 | BR-0023() | Bridge Funds | PE | BRIDGE REPLACEMENT ON SR-23 AT BRANCH OF LITTLE CANOE CREEK (BIN 000226) | 2022 | Exempt | 100000 | 25000 | 125000 | 2021-12-08
ALDOT | Add new project | 100073844 | BR-0023() | Bridge Funds | RW | BRIDGE REPLACEMENT ON SR-23 AT BRANCH OF LITTLE CANOE CREEK (BIN 000226) | 2022 | Exempt | 28000 | 7000 | 35000 | 2021-12-08
St. Clair County | Add $595,430 CMAQ funding | 100070990 | CMAQ-0025(558) | Congestion Mitigation Air Quality | RW | INTERSECTION IMPROVEMENTS ON SR-25(US-411) AT CR-6(SANIE ROAD/SIMPSON ROAD) PHASE 2 | 2022 | Exempt | 777229.6 | 194307.4 | 971537 | 2021-12-08
Bessemer | Add $59,322 STPBH funding | 100006322 | M-7008(002) | Surface Transportion Program Birmingham Attributable(STPBH) | RW | I-59 ACCESS RD FROM HICKORY DR TO 4TH AVE. | 1981 | Exempt | 98560 | 33015 | 131575 | 2021-12-08
ALDOT | Move to FY2022 | 100048415 | APDF-1602(542) | Appalachian Development Highway System | CN | BIRMINGHAM NORTHERN BELTLINE PARTIAL EASTBOUND BASE AND PAVE FROM SR 79 TO SR 75; EASTBOUND MAINLINE BRIDGES AND SINGLE RAMP BRIDGE B AT SR 79 | 2022 | Non-Exempt* | 67600000 | 0 | 67600000 | 2022-03-09
ALDOT | Add new project | 100074432 | ST-037-I59-013 | State Funds | CN | REPAIR AND REPLACEMENTS OF ENTRANCE AND EXIT RAMPS ON I-59/20 AT MCASHAN DRIVE | 2022 | Exempt | 0 | 2109186 | 2109186 | 2022-03-09
ALDOT | Add new project | 100074394 | RACR-059-003-008 | State Funds | CN | CONCRETE PAVEMENT FROM SR-3 (US-31) TO SR-25 OUTSIDE SOUTHBOUND LANES | 2022 | Exempt | 0 | 300000 | 300000 | 2022-03-09
ALDOT | Move outside TIP | 100049955 | BR-0119(513) | Bridge Funds | CN | REPLACE BRIDGE, BIN 001308, SR-119 OVER SHEPARD BRANCH (SUFF=56.3, STATUS=FO) | - | Exempt | 2385988 | 596497 | 2982485 | 2022-03-09
ALDOT | Delete | 100040770 | STPBHF-7026() | Surface Transportion Program Birmingham Attributable | UT | CR-2303 (LAKESHORE PKWY) AT I-65 INTERCHANGE MODIFICATIONS. | - | Exempt | 179978.4 | 44994.6 | 224973 | 2022-03-09
ALDOT | Delete | 100049209 | HPP-A139() | High Priority and Congressional Earmark Projects | RW | HELENA BYPASS FROM CR-52 WEST OF HELENA TO SR-261 NORTH OF HELENA | - | Non-Exempt* | 1944844.8 | 486211.2 | 2431056 | 2022-03-09
ALDOT | Delete | 100049210 | HPP-A139() | High Priority and Congressional Earmark Projects | UT | HELENA BYPASS FROM CR-52 WEST OF HELENA TO SR-261 NORTH OF HELENA | - | Non-Exempt* | 116788.8 | 29197.2 | 145986 | 2022-03-09
Irondale | Move outside TIP | 100032397 | CMAQ-9802() | Congestion Mitigation Air Quality | RW | >SHADES CREEK GREENWAY MULTI-USE TRAIL SHADES CREEK GREENWAY - 1. ON-ROAD CONNECTION VIA ELDER STREET MONCLAIR ROAD AND CRESTWOOD BLVD FROM 15TH STREET TO 20TH ST. 2. OFF-ROAD TRAIL ALONG SHADESCREEK. CONNECTORS ALONG GREENWAY TRAIL | - | Exempt | 62483.52 | 15620.88 | 78104.4 | 2022-03-09
City of Birmingham | Add $1,081,335 of CMAQ funding | 100064294 | TAPBH-CMAQ 3715 (262) | Congestion Mitigation Air Quality | CN | STREETSCAPE IMPROVEMENTS ALONG 2ND AVE S FROM 24TH ST S TO 32ND ST S, 27TH ST S FROM 2ND AVE S TO 3RD AVE S, AND 29TH ST S FROM 2ND AVE S TO 3RD AVE S | 2022 | Exempt | 2081335.2 | 520333.8 | 2601669 | 2022-03-09 | #REF!
City of Birmingham | Add $80,000 of STPBH funding | 100056314 | STPBH-7117(600) | Surface Transportion Program Birmingham Attributable | PE | STREETSCAPE AND TRANSPORTATION IMPROVEMENTS ON 16TH STREET CORRIDOR FROM 11TH AVE NORTH TO I-65 WITHIN FOUNTAIN HEIGHTS NEIGHBORHOOD | 2014 | Exempt | 320000 | 80000 | 400000 | 2022-03-09 | #REF!
Center Point | Add $1,672,184 of STPBH funding | 100054521 | STPBH-3716(250) | Surface Transportion Program Birmingham Attributable | CN | RESURFACING, SIDEWALK ADDITIONS AND DRAINAGE IMPROVEMENTS ALONG POLLY REED ROAD FROM SR-75 TO REED ROAD NE | 2022 | Exempt | 6376184.816 | 1594046.204 | 7970231.02 | 2022-03-09
Hoover | Add $638,625 of CMAQ funding | 100056541 | CMAQ-7282(600) | Congestion Mitigation Air Quality | CN | SIDEWALK ALONG CR-1142 (CHAPEL ROAD) FROM PARK AVE TO STONE BROOK PKWY (CITY OF HOOVER) | 2022 | Exempt | 1487841.6 | 371960.4 | 1859802 | 2022-03-09
Bessemer | Add $1,400,786 of CMAQ funding | 100064230 | CMAQ-3715(270) | Congestion Mitigation Air Quality | CN | PEDESTRIAN BRIDGE OVER SR-150 BETWEEN BERKLEY AVE AND CLARENDON AVE - CITY OF BESSEMER | 2022 | Exempt | 3631048 | 907762 | 4538810 | 2022-03-09
RPCGB | Add $1,100,000 of STPBH funding | 100070046 | STPBH-TR19(900) | Surface Transportion Program Birmingham Attributable | SP | BIRMINGHAM RIDE SHARE PROGRAM FY2022-2023 | 2022 | Exempt | 2400000 | 0 | 2400000 | 2022-03-09
Leeds | Add new project | 100074143 | TAPAA-TA22(911) | Transportation Alternative Program Any Area | CN | DOWNTOWN STREETSCAPE IMPROVEMENTS ALONG SR-4 (US-78 / PARKWAY DRIVE) AND SR-25 (US-411 / 9TH STREET) IN LEEDS | 2023 | Exempt | 640000 | 160000 | 800000 | 2022-03-09
Fairfield | Add new project | 100074132 | TAPAA-TA22(910) | Transportation Alternative Program Any Area | CN | SIDEWALKS ALONG MILSTEAD ROAD AND HIGHLAND DRIVE IN THE GLEN OAKS COMMUNITY OF FAIRFIELD | 2023 | Exempt | 529176 | 132294 | 661470 | 2022-03-09
ALDOT | Move to FY2022 | 100048415 | APDF-1602(542) | Appalachian Development Highway System | CN | BIRMINGHAM NORTHERN BELTLINE PARTIAL EASTBOUND BASE AND PAVE FROM SR 79 TO SR 75; EASTBOUND MAINLINE BRIDGES AND SINGLE RAMP BRIDGE B AT SR 79 | 2022 | Non-Exempt* | 67600000 | 0 | 67600000 | 2022-03-09
ALDOT | Add new project | 100074432 | ST-037-I59-013 | State Funds | CN | REPAIR AND REPLACEMENTS OF ENTRANCE AND EXIT RAMPS ON I-59/20 AT MCASHAN DRIVE | 2022 | Exempt | 0 | 2109186 | 2109186 | 2022-03-09
ALDOT | Add new project | 100074394 | RACR-059-003-008 | State Funds | CN | CONCRETE PAVEMENT FROM SR-3 (US-31) TO SR-25 OUTSIDE SOUTHBOUND LANES | 2022 | Exempt | 0 | 300000 | 300000 | 2022-03-09
ALDOT | Move outside TIP | 100049955 | BR-0119(513) | Bridge Funds | CN | REPLACE BRIDGE, BIN 001308, SR-119 OVER SHEPARD BRANCH (SUFF=56.3, STATUS=FO) | - | Exempt | 2385988 | 596497 | 2982485 | 2022-03-09
ALDOT | Delete | 100040770 | STPBHF-7026() | Surface Transportion Program Birmingham Attributable | UT | CR-2303 (LAKESHORE PKWY) AT I-65 INTERCHANGE MODIFICATIONS. | - | Exempt | 179978.4 | 44994.6 | 224973 | 2022-03-09
ALDOT | Delete | 100049209 | HPP-A139() | High Priority and Congressional Earmark Projects | RW | HELENA BYPASS FROM CR-52 WEST OF HELENA TO SR-261 NORTH OF HELENA | - | Non-Exempt* | 1944844.8 | 486211.2 | 2431056 | 2022-03-09
ALDOT | Delete | 100049210 | HPP-A139() | High Priority and Congressional Earmark Projects | UT | HELENA BYPASS FROM CR-52 WEST OF HELENA TO SR-261 NORTH OF HELENA | - | Non-Exempt* | 116788.8 | 29197.2 | 145986 | 2022-03-09
Irondale | Move outside TIP | 100032397 | CMAQ-9802() | Congestion Mitigation Air Quality | RW | >SHADES CREEK GREENWAY MULTI-USE TRAIL SHADES CREEK GREENWAY - 1. ON-ROAD CONNECTION VIA ELDER STREET MONCLAIR ROAD AND CRESTWOOD BLVD FROM 15TH STREET TO 20TH ST. 2. OFF-ROAD TRAIL ALONG SHADESCREEK. CONNECTORS ALONG GREENWAY TRAIL | - | Exempt | 62483.52 | 15620.88 | 78104.4 | 2022-03-09
City of Birmingham | Add $1,081,335 of CMAQ funding | 100064294 | TAPBH-CMAQ 3715 (262) | Congestion Mitigation Air Quality | CN | STREETSCAPE IMPROVEMENTS ALONG 2ND AVE S FROM 24TH ST S TO 32ND ST S, 27TH ST S FROM 2ND AVE S TO 3RD AVE S, AND 29TH ST S FROM 2ND AVE S TO 3RD AVE S | 2022 | Exempt | 2081335.2 | 520333.8 | 2601669 | 2022-03-09 | #REF!
City of Birmingham | Add $80,000 of STPBH funding | 100056314 | STPBH-7117(600) | Surface Transportion Program Birmingham Attributable | PE | STREETSCAPE AND TRANSPORTATION IMPROVEMENTS ON 16TH STREET CORRIDOR FROM 11TH AVE NORTH TO I-65 WITHIN FOUNTAIN HEIGHTS NEIGHBORHOOD | 2014 | Exempt | 320000 | 80000 | 400000 | 2022-03-09 | #REF!
Center Point | Add $1,672,184 of STPBH funding | 100054521 | STPBH-3716(250) | Surface Transportion Program Birmingham Attributable | CN | RESURFACING, SIDEWALK ADDITIONS AND DRAINAGE IMPROVEMENTS ALONG POLLY REED ROAD FROM SR-75 TO REED ROAD NE | 2022 | Exempt | 6376184.816 | 1594046.204 | 7970231.02 | 2022-03-09
Hoover | Add $638,625 of CMAQ funding | 100056541 | CMAQ-7282(600) | Congestion Mitigation Air Quality | CN | SIDEWALK ALONG CR-1142 (CHAPEL ROAD) FROM PARK AVE TO STONE BROOK PKWY (CITY OF HOOVER) | 2022 | Exempt | 1487841.6 | 371960.4 | 1859802 | 2022-03-09
Bessemer | Add $1,400,786 of CMAQ funding | 100064230 | CMAQ-3715(270) | Congestion Mitigation Air Quality | CN | PEDESTRIAN BRIDGE OVER SR-150 BETWEEN BERKLEY AVE AND CLARENDON AVE - CITY OF BESSEMER | 2022 | Exempt | 3631048 | 907762 | 4538810 | 2022-03-09
RPCGB | Add $1,100,000 of STPBH funding | 100070046 | STPBH-TR19(900) | Surface Transportion Program Birmingham Attributable | SP | BIRMINGHAM RIDE SHARE PROGRAM FY2022-2023 | 2022 | Exempt | 2400000 | 0 | 2400000 | 2022-03-09
Leeds | Add new project | 100074143 | TAPAA-TA22(911) | Transportation Alternative Program Any Area | CN | DOWNTOWN STREETSCAPE IMPROVEMENTS ALONG SR-4 (US-78 / PARKWAY DRIVE) AND SR-25 (US-411 / 9TH STREET) IN LEEDS | 2023 | Exempt | 640000 | 160000 | 800000 | 2022-03-09
Fairfield | Add new project | 100074132 | TAPAA-TA22(910) | Transportation Alternative Program Any Area | CN | SIDEWALKS ALONG MILSTEAD ROAD AND HIGHLAND DRIVE IN THE GLEN OAKS COMMUNITY OF FAIRFIELD | 2023 | Exempt | 529176 | 132294 | 661470 | 2022-03-09
Birmingham | Delete | 100064216 | STPBH-3716(253) | Surface Transportion Program Birmingham Attributable | CN | UPGRADE AND REPLACE INTERSTATE LIGHTING ALONG I-20/59 FROM 3700 EAST OF THE EB STEPHENS EXPRESSWAY INTERCHANGE TO 2000 EAST OF THE I-20/59 SPLIT | - | Exempt | 1106162.4 | 276540.6 | 1382703 | 2022-05-11
ALDOT | Add $1,106,162 of STPBH funding | 100071977 | NH-CMAQ 0003 (630) | NHS, CMAQ, and STPBH | FM | RESURFACING AUXILIARY LANES RAMP IMPROVEMENTS MEDIAN BARRIER RAIL AND BRIDGE RAIL RETROFITS ON SR-3 (US-31) FROM BONITA DRIVE TO 2ND AVE SOUTH | 2021 | Exempt | 8713415.15 | 968157.2389 | 9681572.3889 | 2022-05-11
ALDOT | Add $1,156,897 to cover overruns | 100068066 | IM-I020(356) | Interstate Maintenance | CN | PAVEMENT REHABILITATION ON I-20 FROM EXIT 140 TO THE ST. CLAIR COUNTY LINE | 2020 | Exempt | 8000000 | 0 | 8000000 | 2022-05-11
ALDOT | Add new project | 100074990 | BR-0007() | Bridge Funds | PE | BRIDGE REPLACEMENT ON SR-7 (US-11) OVER THE LITTLE CAHABA RIVER (BIN 000486) | 2022 | Exempt | 155200 | 38800 | 194000 | 2022-05-11
St. Clair County | Add new project | 100074499 | ATRP2-58-2022-058 | ATRIP2 | PE | ADDING TURN LANES ON SR-25 (US-411) AT KERR ROAD; ALSO ADDING RIGHT TURN LANE ON KERR ROAD | 2022 | Exempt | 0 | 20000 | 20000 | 2022-05-11
St. Clair County | Add new project | 100075092 | ATRP2-58-2022-058 | ATRIP2 | CN | ADDING TURN LANES ON SR-25 (US-411) AT KERR ROAD; ALSO ADDING RIGHT TURN LANE ON KERR ROAD | 2023 | Exempt | 0 | 1649158 | 1649158 | 2022-05-11
ALDOT | Add new project | 100074775 | RHCH-RR22() | Rail Road Safety Funds | CN | RR XING HAZARD ELIMINATION IMPROVEMENTS FOR THE INSTALLATION OF SIGNALS, GATES, BELLS, SIGNS, LEGEND AND MARKINGS AT CR-26 (FULTON SPRINGS ROAD) AND CSX RAILROAD DOT NO 352277T | 2022 | Exempt | 301372.2 | 33485.8 | 334858 | 2022-05-11
ALDOT | Move outside TIP | 100071723 | IM-I459() | Interstate Maintenance | CN | PLANING, OVERLAY AND STRIPING ON I-459 FROM THE NORTH END OF THE BRIDGE OVER SR-150 TO THE SOUTH END OF THE BRIDGE OVER US-31 | 2025 | Exempt | 2348747.1 | 260971.9 | 2609719 | 2022-05-11
ALDOT | Move outside TIP | 100049957 | BR-0004() | Bridge Funds | CN | REPLACE BRIDGE, BIN 000884, SR-4 (US-78) OVER LITTLE CAHABA RIVER (SUFF=58.4, STATUS=FO) | 2024 | Exempt | 2691994 | 672998.5 | 3364992.5 | 2022-05-11
ALDOT | Delete | 100003818 | BR-7044(600) | Bridge Funds | PE | BR REPL AND APP ON SR-3 (US-31) BIN# 002243 OVER SOU RR #3-37-15.8B | - | Exempt | 125605.6 | 31401.4 | 157007 | 2022-05-11
RPCGB | Add new project | 100075339 | TBD | American Rescue Plan (ARP) | TR | Operational Expenses for 5310 projects | 2022 | Exempt | 125367 | 0 | 125367 | 2022-05-11
Clastran | Add New Project | 100075291 | TBD | Carbon Reduction Program | TR | FLEXIBLE FUNDS TRANSFER TO FTA FOR PARATRANSIT CONSORTIUM - PURCHASED TRANSPORTATION | 2023 | Exempt | 1000000 | 250000 | 1250000 | 2022-05-11
Hoover | Delete | 100056540 | CMAQ-7282() | Congestion Mitigation Air Quality | UT | SIDEWALK ALONG CR-1142 (CHAPEL ROAD) FROM PARK AVE TO STONE BROOK PKWY (CITY OF HOOVER) | 2022 | Exempt | 90041 | 22510.25 | 112551.25 | 2022-05-11
Hoover | Add $401,061 of CMAQ funding | 100056541 | CMAQ-7282(600) | Congestion Mitigation Air Quality | CN | SIDEWALK ALONG CR-1142 (CHAPEL ROAD) FROM PARK AVE TO STONE BROOK PKWY (CITY OF HOOVER) | 2022 | Exempt | 1888902.4 | 472225.6 | 2361128 | 2022-05-11
Vestavia Hills | Add $240,000 of MPO TAP funding | 100062997 | TAPAA-TA14(931) | MPO and ALDOT Transportation Alternative Program | CN | SICARD HOLLOW ROAD TUNNEL SAFE ROUTE FOR NON-DRIVERS. THIS PROJECT IS LOCATED AT A TUNNEL TO BE CONSTRUCTED UNDER SICARD HOLLOW ROAD IN LIBERTY PARK | 2017 | Exempt | 978966.4 | 244741.6 | 1223708 | 2022-05-11
ALDOT | Move inside TIP | 100073849 | CRPAA-MR21() | Carbon Reduction Program Any Area | SP | 5-YEAR RTOP TRAFFIC OPERATIONS PROGRAM (RTOP) ON ALL U.S. AND SR. SIGNALIZED INTERSECTIONS IN JEFFERSON AND SHELBY COUNTIES YEAR 2023 AND 2024 | 2022 | Exempt | 1502249.6 | 375562.4 | 1877812 | 2022-08-10
ALDOT | Add new project | 100074910 | CRPAA-I059() | Carbon Reduction Program Any Area | PE | THE INSTALLATION OF ITS DEVICES AND NETWORK INFRASTRUCTURE TO SUPPORT ADVANCED CORRIDOR MANAGEMENT (ALGO, TSMO) ON I-20/59 | 2022 | Exempt | 52000 | 13000 | 65000 | 2022-08-10
ALDOT | Add new project | 100074911 | CRPAA-I059() | Carbon Reduction Program Any Area | CN | THE INSTALLATION OF ITS DEVICES AND NETWORK INFRASTRUCTURE TO SUPPORT ADVANCED CORRIDOR MANAGEMENT (ALGO, TSMO) ON I-20/59 | 2022 | Exempt | 3600000 | 900000 | 4500000 | 2022-08-10
ALDOT | Add new project | 100075303 | STPAA-NR23() | Carbon Reduction Program Any Area | SP | REGIONAL TRANSPORTATION MANAGEMENT CENTER AND ASAP PROGRAM FOR FY-2023 | 2023 | Exempt | 2400000 | 600000 | 3000000 | 2022-08-10
ALDOT | Move inside TIP | 100055415 | IM-I065() | Interstate Maintenance | CN | CONCRETE PAVEMENT REHAB, UNDERSEAL, GRINDING, PAVERLAID SURFACE TREATMENT, UNDERDRAIN, SHOULDER PAVEMENT,GUARDRAIL ON I-65 FROM US-31 TO RALEIGH AVENUE. OVERPASS (PRIORITY #35) | 2023 | Exempt | 7544622.6 | 838291.4 | 8382914 | 2022-08-10
ALDOT | Add new project | 100074409 | IAR-037-000-009 | State Funds | CN | RELOCATION OF LAKESHORE PARKWAY AND MORGAN ROAD FROM CUMBERLAND ROAD TO APPROXIMATELY 1000 FEET FROM TURIN DRIVE | 2023 | Exempt | 0 | 4000000 | 4000000 | 2022-08-10
ALDOT | Add new project | 100075137 | IM-I059() | Interstate Maintenance | CN | I-59 BRIDGE RAIL RETROFIT BETWEEN VALLEY ROAD AND SR-5 (ARKADELPHIA ROAD) AT BIN'S 14388, 14389, 14390, 14381, 14758 AND 14759 | 2023 | Exempt | 454500 | 50500 | 505000 | 2022-08-10
ALDOT | Add new project | 100075226 | IM-I059() | Interstate Maintenance | PE | CONCRETE PAVEMENT REHABILITATION ON I-59 FROM THE NORTH END OF THE BRIDGE (BIN 10496) OVER VANDERBILT ROAD TO THE NORTH END OF THE BRIDGE(BIN 11095) OVER AVIATION AVENUE | 2022 | Exempt | 465497.1 | 51721.9 | 517219 | 2022-08-10
ALDOT | Add new project | 100073714 | NH-0007() | National Highway System | FM | RESURFACING, PLANING, STRIPING AND PATCHING ON SR-7 (US-11) FROM 25TH STREET NORTH TO 83RD STREET NORTH INCLUDING WORK ON RAMPS 130A AND 130B | 2023 | Exempt | 2364577.6 | 591144.4 | 2955722 | 2022-08-10
ALDOT | Add new project | 100075458 | ST-037-I59-015 | State Funds | SP | START-UP PERIOD FUNDING AND FIRST YEAR OPERATING DEFICIT FOR CITYWALK | 2022 | Exempt | 0 | 1300000 | 1300000 | 2022-08-10
ALDOT | Add new project | 100074775 | RHCH-RR22() | Rail Road Safety Funds | CN | RR XING HAZARD ELIMINATION IMPROVEMENTS FOR THE INSTALLATION OF SIGNALS, GATES, BELLS, SIGNS, LEGEND AND MARKINGS AT CR-26 (FULTON SPRINGS ROAD) AND CSX RAILROAD DOT NO 352277T | 2022 | Exempt | 301372.2 | 33485.8 | 334858 | 2022-08-10
ALDOT | Add new project | 100075388 | RHCH-RR22() | Rail Road Safety Funds | CN | RAILROAD XING HAZARD ELIMINATION IMPRV, OBS EQUIP REPLACE EXISTING ACTIVE WARNING DEVICES WITH TWO (2) 12K DEEP DISH LENSES WITH LIGHT EMITTING DIODES (LED), TWO (2) GATES, TWO (2) BELLS AND CWT AT 5TH STREET AND BNSF; REF. # 2214HE; DOT # 664848X. | 2022 | Exempt | 263464.2 | 29273.8 | 292738 | 2022-08-10
ALDOT | Add new project | 100075258 | RHCH-RR22() | Rail Road Safety Funds | CN | RR XING HAZARD ELIMINATION IMPROVEMENT FOR THE REPLACEMENT OF INCANDESCENT LIGHTS TO LIGHT EMITTING DIODES (LED) 12" LENSES AT DOT NO. 663652A ON AVENUE W IN BIRMINGHAM; BNSF RAILROAD; REF. # 2212HE. | 2022 | Exempt | 45000 | 5000 | 50000 | 2022-08-10
ALDOT | Move outside TIP | 100071723 | IM-I459() | Interstate Maintenance | CN | PLANING, OVERLAY AND STRIPING ON I-459 FROM THE NORTH END OF THE BRIDGE OVER SR-150 TO THE SOUTH END OF THE BRIDGE OVER US-31 | 2025 | Exempt | 2348747.1 | 260971.9 | 2609719 | 2022-08-10
ALDOT | Move outside TIP | 100073344 | IM-I459() | Interstate Maintenance | CN | CONCRETE PAVEMENT RECONSTRUCTION ON I-459 FROM LORNA ROAD (MP14.794) TO WEST OF LITTLE SHADES CREEK (MP 15.892) | 2024 | Exempt | 25963585.2 | 2884842.8 | 28848428 | 2022-08-10
Homewood | Add $2,877,943 of CMAQ funding | 100029525 | CMAQ-9802(911) | Congestion Mitigation Air Quality and Carbon Reduction Funding | CN | SHADES CREEK GREENWAY MULTI-PURPOSE TRAIL - PHASE TWO GRADE, DRAIN, BASE, PAVE, BRIDGE, STRIPING, SIGNING AND LANDSCAPING CITY OF HOMEWOOD JEFFERSON COUNTY | 2022 | Exempt | 7064597.6 | 1766149.4 | 8830747 | 2022-08-10
Jefferson County | Move outside TIP | 100007540 | STPBH-5939(200) | Surface Transportion Program Birmingham Attributable | CN | WIDEN CR-29\1277 FROM CR-370 (HEATHERWOOD DR) TO CR-2311 (ACTON ROAD) AND BRG REPLACEMENT OVER CAHABA RIVER BIN #019329 | 2024 | Non-Exempt* | 1588654.4 | 397163.6 | 1985818 | 2022-08-10
Jefferson County | Add Utility Phase | 100075679 | STPBH-5939() | Surface Transportion Program Birmingham Attributable | UT | WIDEN CR-29\1277 FROM CR-370 (HEATHERWOOD DR) TO CR-2311 (ACTON ROAD) AND BRG REPLACEMENT OVER CAHABA RIVER BIN #019329 | 2023 | Non-Exempt* | 1600000 | 400000 | 2000000 | 2022-08-10
Center Point | Add $1,851,421 of STPBH funding | 100054521 | STPBH-3716(250) | Surface Transportion Program Birmingham Attributable | CN | RESURFACING, SIDEWALK ADDITIONS AND DRAINAGE IMPROVEMENTS ALONG POLLY REED ROAD FROM SR-75 TO REED ROAD NE | 2022 | Exempt | 8227605.6 | 2056901.4 | 10284507 | 2022-08-10
Center Point | Add new project | 100074808 | RALG-37-2022-135 | Rebuild Alabama | CN | RESURFACE POLLY REED ROAD FROM HILLCREST ROAD TO OLD SPRINGVILLE ROAD AND HILLCREST ROAD FROM POLLY REED ROAD TO MARY VANN LANE | 2022 | Exempt | 0 | 250000 | 250000 | 2022-08-10
City of Pelham | Move outside TIP | 100039450 | STPBH-7012() | Surface Transportion Program Birmingham Attributable | CN | PELHAM TOPICS, SR-3(US-31) FROM CR-52 TO A POINT 0.25 MILES NORTH OF CR-105 (PHASE II) | 2024 | Non-Exempt* | 449008.8 | 112252.2 | 561261 | 2022-08-10
City of Pelham | Add $240,000 of STPBH funding | 100039466 | STPBH-7012(602) | Surface Transportion Program Birmingham Attributable | PE | PELHAM TOPICS, SR-3(US-31) FROM CR-52 TO A POINT 0.25 MILES NORTH OF CR-105 (PHASE II) | 2001 | Non-Exempt* | 939016 | 234754 | 1173770 | 2022-08-10
Shelby County | Add $120,000 of STPBH funding | 100056308 | STPBH-5914(250) | Surface Transportion Program Birmingham Attributable | PE | BRIDGE REPLACEMENT ON CR-55 OVER NORFOLK SOUTHERN RAILROAD NEAR STERRETT BIN 10357 | 2014 | Exempt | 436420 | 109105 | 545525 | 2022-08-10
Hueytown | Add $550,000 of STPBH funding | 100056288 | STPBH-7021(600) | Surface Transportion Program Birmingham Attributable | RW | CR-46 (HUEYTOWN ROAD) ADDITIONAL TURN LANES AND INTERSECTION IMPROVEMENTS FROM WALKER AVENUE TO NORTH OF HILLSIDE DRIVE | 2017 | Exempt | 1068000 | 267000 | 1335000 | 2022-08-10
City of Birmingham | Move outside TIP | 100069761 | CMAQ-NR19() | Congestion Mitigation Air Quality | CN | STREETSCAPE AND SIDEWALK ENHANCEMENTS INCLUDING ADA UPGRADES IN MORE THAN 20 LOCATIONS THROUGHOUT THE CITY OF BIRMINGHAM; INFORMATION ABOUT SPECIFIC LOCATIONS WILL BE PROVIDED UPON REQUEST | 2024 | Exempt | 2102020 | 525505 | 2627525 | 2022-08-10
City of Birmingham | Move outside TIP | 100066709 | CMAQ-3717() | Congestion Mitigation Air Quality | CN | WOODLAWN NEIGHBORHOOD STREETSCAPE PHASE 2 (CITY OF BIRMINGHAM) | 2024 | Exempt | 1286562.4 | 321640.6 | 1608203 | 2022-08-10
Vestavia Hills | Add $204,827 of CMAQ funding | 100050996 | DE-IBRD-A104(916) | Congestion Mitigation Air Quality | PE | VESTAVIA HILLS PEDESTRIAN WALKWAY INCLUDING THE WALD PARK PEDESTRIAN CROSSOVER ON US-31 | 2008 | Exempt | 404827.2 | 101206.8 | 506034 | 2022-08-10